## Slide 1: Platform Evolution Project Weekly Project Update
11th August 2022

## Slide 2
Agenda
01
PEV Progress Summary & Plan
02
IT Design & Preparation
03
04
Data Model

## Slide 3
PEV – Overall Progress Report Summary (11th August)
Summary Status | Workstream | RAG | Budget
The Business Design phase has now been completed. Handover of Business Design documentation to the IT team has been completed for all Processes and the End to End Process / Initial Requirement Prioritisation document. IT workshops and Playback sessions have been completed for Process 1, 2, 3, 4 & 5. | IT Design & Preparation |  | 
 | Data Model |  | 
Risks & Issues
Described on slide 4.
Decisions
Decision on ongoing feature deployments and enhancements in CDMS will cause re-estimation and not attaining steady-state. We need to decide on the stability other solution? – Rolly / Antonico
IT Design & CDMS | Data Model
Completed process 1 to 5 successfully. Process 6 and 7 are in progress. Completed analysis of the production sites First draft completed for HLD Walkthrough of to-be flows with Italy, pending further discussions & review Second session - France CDMS users - business process clarifications Discussions related to integration with Avanade, Bitrock and GOSP | Workshops with Generali held on 2nd and 4th August Progress against the 4 domains Organisation, Contract and Risk Domains will have a second draft on 05/08 Cross Reference Domain is ongoing and will have a structure review by 12/08

## Slide 4
PEV – Overall Progress Report Risks & Issues (8th August)
IT Design & CDMS Risks
None
IT Design & CDMS Issues
None

## Slide 5
MAY 22
02-06
09-13
16-20
23-27
30-03
JULY 22
04-08
11-15
18-22
25-29
SEPTEMBER 22
05-09
12-16
19-23
26-30
JUNE 22
06-10
13-17
20-24
27-01
AUGUST 22
01-05
08-12
15-19
22-26
29-02
1 – PRE-SALES MANAGEMENT
2 – SUBMISSION MANAGEMENT
3 – SUBMISSION PRE-QUALIFICATION & FEASIBILITY
4 – UNDERWRITING PACKAGE
5 – PRICING & RISK ASSESSMENT
6 – REINSURANCE
7 – QUOTING & RISK BINDING
WORKFLOW CONTENTS
PRIORITISATION & PLAYBACK END-TO-END
IT Design Workshop Completed
IT Design Workshop To Do
Today
8 - DATA MODEL ANALYSIS
9 - POST BIND CDMS
END TO END ROADMAP PLANNING
Foundation Workshop Approach
IT Design & Preparation
Each Macro process has 6 workshops
Business Process, Solution Design and Product backlog captured
Overall Programme
Design
PEV – Overall Workshop Plan (4th August)
IT Design Workshop in Progress

## Slide 6
Agenda
01
PEV Progress Summary & Plan
02
02
IT Design & Preparation
03
Data Model

## Slide 7
IT Design & Preparation – Report Summary (4th August)
7
Business Design Documentation Progress |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Processes & RAG |  |  | High level Solution design document |  |  | Product Backlog |  |  | Technical Integration document |  |  | Comments |  | 
Processes | Processes | RAG | Planned End Date | Revised / Actual End Date | %Complete | Planned End Date | Revised / Actual End Date | %Complete | Planned End Date | Revised / Actual End Date | %Complete | Approved? | Comments | Support Needed
1 | Pre-Sales |  | 28-Jun-22 | 29-Jun-22 | 100% | 28-Jun-22 | 29-Jun-22 | 100% | N/A | N/A | N/A | Yes |  | 
2 | Submission Management |  | 05-Jul-22 | 05-Jul-22 | 100% | 05-Jul-22 | 05-Jul-22 | 100% | N/A | N/A | N/A | Yes |  | 
3 | Sub Prequalification Feasibility |  | 08-Jul-22 | 08-Jul-22 | 100% | 08-Jul-22 | 08-Jul-22 | 100% | N/A | N/A | N/A | Yes |  | 
4 | Underwriting Package |  | 18-Jul-22 | 18-Jul-22 | 100% | 18-Jul-22 | 18-Jul-22 | 100% | N/A | N/A | N/A | Yes |  | 
5 | Pricing & Rating Assessment |  | 25-Jul-22 | 09-Aug-22 | 100% | 25-Jul-22 | 09-Aug-22 | 100% | N/A | N/A | N/A | Yes |  | 
6 | Reinsurance |  | 01-Aug-22 | 11-Aug-22 | 70% | 01-Aug-22 | 11-Aug-22 | 70% | N/A | N/A | N/A |  |  | 
7 | Quoting & Risk Binding |  | 03-Aug-22 | 24-Aug-22 | 40% | 03-Aug-22 | 24-Aug-22 | 40% | N/A | N/A | N/A |  |  | 
Decision on ongoing feature deployments and enhancements in CDMS will cause re-estimation and not attaining steady-state. We need to decide on the stability other solution? – Rolly / Antonico
Support/Decisions Required

## Slide 8
IT Design – Financials
Nr. of persons for each seniority level | Workstream | Discipline | Name | Country | Estimated person-days | Standard rates £/day | Estimated total (expenses excluded )
1 | Across | Programme Manager | Adam Ward | UK | 10 | 1500 | £15,000.00
1 | Across | Engagement Manager | Anamika Desai | UK | 26 | 1175 | £30500
1 | Across | Enterprise Architect | Riccardo Gozzi | UK | 15 | 1500 | £22,500.00
1 | CRM | Technical Lead | Bharath Samraj | UK | 30 | 825 | £24,750.00
1 | CRM | CRM Functional Consultant | Ucee Akuanyionwu | UK | 35 | 750 | £26,250.00
1 | CRM | Technical Architect | Sejal Shah | Offshore | 32 | 285 | £9,120.00
1 | CRM | Data Analyst (Data Migration) | Arun Kumar | Offshore | 35 | 275 | £9,625.00
1 | SharePoint | Migration Lead | Azher Mohammed | Offshore | 33 | 275 | £9,075.00
1 | SharePoint | Technical Architect | Vaibhav Telore | Offshore | 34 | 285 | £9,690.00
1 | SharePoint | SharePoint Technical Analyst | Sudipta Basu | UK | 34 | 600 | £20,400.00
1 | Across | Test Lead | TBC | Offshore | 20 | 285 | £5,700.00
Sub Total |  |  |  |  |  |  | £182,660
Discount 14% |  |  |  |  |  |  | £ 25,572.40
Total |  |  |  |  |  |  | £157,087.60
Notes: Estimate to Complete
Days
Rate
Cost
Engagement Manager
UK
Anamika Desai
39
1175
45825
Enterprise Solution Architect
UK
TBC
15
1175
17625
Technical Architect
Offshore
Sejal Shah
39
285
11115
Migration Lead
Offshore
Azher Mohammed
40
275
11000
SharePoint Technical Analyst
UK
Sudipta Basu
40
600
24000
CRM Functional Consultant
UK
Ucce Akuanyionwu
40
750
30000
Technical Lead
UK
Bharath Samraj
40
825
33000
Technical Architect
Offshore
Vaibhav Telore
40
285
11400
183965

## Slide 9
Agenda
01
PEV Progress Summary & Plan
02
02
IT Design & Preparation
03
Data Model

## Slide 10
Data Model – Report Summary (4th August)
10
Risk, Organisation, Contract LDM
  Released the second version for the LDM+ Taxonomy for Contract, Risk, Organisation domains.
    Released the collection of all attributes mapped in the current LDM by domain
    The review scheduled for the Cross Reference Domain on 12/08
None
Support/Decisions Required
Data Model Progress Summary |  |  | 
Domains | Processes | Status Update | Comment
1 | Organisation Domain | Completed : Second draft delivery planned for 05/8 | Details Shown below
2 | Contract Domain | Completed : Second draft delivery planned for 05/8 | Details Shown below
3 | Risk Domain | Completed : Second draft delivery planned for 05/8 | Details Shown below
4 | Cross Reference Domain | Structure Review with DBA Team | Validation Review planned by 12/08