## Cover page
Application | No. of Test cases | Execution efforts (in Person Days) | Script update efforts (in Person Days)
Policycenter | 885 | 25.5 | 7
Billingcenter | 585 | 24.15 | 0
Totals | 1470 | 49.65 | 7
Application | No. of Test cases for manual execution | No. of Test cases automation execution (Person Days) | Manual Efforts needed for execution (Person Days) | Automation efforts needed for execution (Person Days) | Total efforts needed for execution (Person Days)
Policycenter | 314 | 571 | 16 | 9.5 | 25.5
Billingcenter | 316 | 269 | 15.25 | 8.9 | 24.15
Totals | 630 | 840 | 31.25 | 18.4 | 49.65

## PC
Functionality Type | Type / Functionality | User stories list | Implementation Type | Test execution type | No. of Test cases | Effort for execution (in Person days) | Effort for Updating the scripts (in Person days)
A. Product specific changes | Product model Marketable products Visibility & editablility conditions OEP | GPS-14143 | New implemetation | Automated | 28 | 0.5 | 0
|  | GPS-14089 | New implemetation | Automated | 28 | 0,5 | 0
|  | GPS-14866 | New implemetation | Manual | 15 | 0.5 | NA
|  | GPS-14286 | New implemetation | Manual | 12 | 0.5 | NA
|  | GPS-23550 | New implemetation | Automated | 18 | 0.5 | 0
B. No changes for Cyber compared to ML/FI | Account / submission creation and update | GPS-14876, GPS-20089 | Reuse of ML / FI | Automated | 50 | 0.5 | 0
| Broker (Branch Office) & Local PC Broker Contact Creation | GPS-18855 | Reuse of ML / FI | Manual | 13 | 2 | NA
| Term Type,Policy Timezone | GPS-18271 | Reuse of ML / FI | Automated | 58 | 0.5 | 0
| Field level validations on different screens, Market Segment,COB Code, Trifocus Name and other fileds | GPS-15015 & GPS-14312, GPS-17029, GPS-20785 | Reuse of ML / FI | Automated | 50 | 1 | 1
| Coverages, Policy Line Split | GPS-14083 & GPS-14083 | Reuse of ML / FI | Automated | 44 | 0.5 | 0.5
| Commissions, Fees, Discounts, Tax Schedule & Tax Calculations, Multiple Risk locations, Portuguese Broker Stamp Duty, Standard / Default Brokerage, TPI % BPI %, Quote screen validations | GPS-14985, GPS-16305, GPS-14313, GPS-16305 & GPS-14133, GPS-14858 | Reuse of ML / FI | Automated | 73 | 1 | 1
| Bind & Issuance | GPS-17490, GPS-16304 | Reuse of ML / FI | Automated | 15 | 0.5 | 0.5
| Policy change, Premium Impacting Change | GPS-14855 | Reuse of ML / FI | Automated | 22 | 0.5 | 0.5
| Cancellation & Reinstate | GPS-16745, GPS-16744, GPS-16705, GPS-17065 | Reuse of ML / FI | Automated | 15 | 0.5 | 1
| Rewrite | GPS-17191, GPS-17019 | Reuse of ML / FI | Automated | 33 | 0.5 | 0.5
| Coinsurance Without Vertical Pricing | GPS-19529 , GPS-17199 | Reuse of ML / FI | Automated | 40 | 0.5 | 1
| Coinsurance Vertical Pricing | GPS-17186 | Reuse of ML / FI | Partial automated | 32 | 3 | NA
| Contra | GPS-14861 | Reuse of ML / FI | Automated | 20 | 0.75 | 0
| UW Controls | GPS-18366 & GPS-17212 | Reuse of ML / FI | Automated | 40 | 0.5 | 1
| Outward Reinsurance | GPS-17190 | Reuse of ML / FI | Automated | 9 | 0.5 | 0
| Upload docs | GPS-20244 | Reuse of ML / FI | Automated | 10 | 0.25 | 0
| Activity Pattern Uplift | GPS-16303 | Reuse of ML / FI | Automated | 10 | 0.25 | 0
| User Preference - Regional Display View (Common Screens) | GPS-17064 | Reuse of ML / FI | Automated | 8 | 0.25 | 0
C. Exploratory testing | All above mentioned functionalities | All above mentioned stories | Reuse of ML / FI | Manual | 192 | 5 | NA
D. Fixes and CRs (Subset) | CRs and 19 Requirement defects | 20785, 21792, 18855, 23104, 24093, 23747, 23746, 24113, 24112, 24111, 24290 | Reuse of ML / FI | Manual | 50 | 5 | NA
[5 empty] | 885 | 25.5 | 7

## BC
Functionality Type | Type / Functionality | User stories list | Implementation Type | Test execution type | No. of Test cases | Effort for execution (in Person days) | Effort for Updating the scripts (in Person days)
A. No changes for Cyber compared to ML/FI | Policy Summary and Policy Details | GPS-14366 | Reuse of ML/FI | Automated | 1 | 0.25 | 0
| Timezone & Timestamp | GPS-14428 | Reuse of ML/FI | Automated | 1 |  | 0
| Bank Account Details | GPS-14218 | Reuse of ML/FI | Automated | 7 | 0.4 | 0
| Producer Summary Details | GPS-14374 | Reuse of ML/FI | Automated | 1 | 0.25 | 0
| NB Billing Instructions | GPS-14416 | Reuse of ML/FI | Automated | 1 |  | 0
| Manage Policy Charges for NB | GPS-14368 , GPS-14369 | Reuse of ML/FI | Automated | 16 | 0.5 | 0
| Manage Invoices for NB | GPS-14378,GPS-14377,GPS-14393,GPS-18305 | Reuse of ML/FI | Automated | 58 | 1 | 0
| Send NB Invoice details to DPS | GPS-15697 | Reuse of ML/FI | Manual | 5 | 0.25 | NA
| Regenerate Invoice Docs in multiple languages in BC | GPS-21124 | Reuse of ML/FI | Manual | 10 | 0.5 | NA
| Manage Write-off , Negative write-off Transaction & Producer Fund Transfer | GPS-14402,GPS-14376 | Reuse of ML/FI | Automated | 41 | 1 | 0
| Manage Disbursement | GPS-17022 | Reuse of ML/FI | Automated | 10 | 0.5 | 0
| Manage Credit Distributions | GPS-17044 | Reuse of ML/FI | Automated | 9 | 0.5 | 0
| Manage Credit Handling | GPS-14397 | Reuse of ML/FI | Automated | 11 | 0.5 | 0
| Manage Invoices for Policy Change | GPS-16694,GPS-19008 | Reuse of ML/FI | Automated | 20 | 0.5 | 0
| Manage Invoices for OEP | GPS-14386,GPS-17089 | Reuse of ML/FI | Manual | 37 | 2 | NA
| Broker of Record (BoR) Change | GPS-18701 | Reuse of ML/FI | Manual | 8 | 1 | NA
| Send Policy Change Invoice details to DPS | GPS-17135,GPS-17137 | Reuse of ML/FI | Manual | 9 | 1 | NA
| Process BIDAC Policies Cancellation transaction | GPS-14405 | Reuse of ML/FI | Automated | 17 | 0.5 | 0
| Create and manage Invoices for BIDAC Reinstated Policies | GPS-14388 | Reuse of ML/FI | Automated | 12 | 0.5 | 0
| Send Cancellation Details to DPS | GPS-14421 | Reuse of ML/FI | Manual | 6 | 1 | NA
| Manage Invoices for Contra Cancellation & Replace Rewrite | GPS-17835,GPS-17836 | Reuse of ML/FI | Automated | 7 | 0.5 | 0
| Manage Invoices for Contra Override Transactions | GPS-14384 | Reuse of ML/FI | Manual | 14 |  | NA
| Billing instructions from PC for Coinsurance policies | GPS-15846 | Reuse of ML/FI | Automated | 1 |  | 0
| Manage Coinsurance Policy charges | GPS-15847 | Reuse of ML/FI | Automated | 9 | 0.5 | 0
| Manage Invoices for Coinsurance Policies without VERTICAL PRICING - Beazley as Leader & Follower | GPS-15848 | Reuse of ML/FI | Automated | 10 | 0.5 | 0
| Manage Invoices for Coinsurance Policies with VERTICAL PRICING - Beazley as Leader & Follower | GPS-18702 | Reuse of ML/FI | Manual | 12 | 1.5 | NA
| Manage Invoices & allocation for Coinsurance policies - on Policy Change & Cancellation | GPS-20271,GPS-20272 | Reuse of ML/FI | Manual | 22 | 1 | NA
| Send Coinsurance Invoice details to DPS | GPS-15849 | Reuse of ML/FI | Manual | 12 | 1 | NA
| Manage Invoices for Coinsurance policies - Contra Override & Contra - Replace | GPS-20273,GPS-20274,GPS-19047 | Reuse of ML/FI | Manual | 31 | 2 | NA
| Manage Invoicing & Allocation for Dummy Brokers Policies | GPS-16447,GPS-14371 | Reuse of ML/FI | Automated | 27 | 0.5 | 0
| Billing instructions from PC for Outward RI | GPS-18306 | Reuse of ML/FI | Automated | 10 | 0.5 | 0
B. Exploratory testing | All above mentioned functionalities | All above mentioned stories | Reuse of ML / FI | Manual | 130 | 2 | NA
C. Fixes and CRs (Subset) | GPS-23461 - Requirement Defect: Producer Code Should Not Be Displayed in BillingCenter UI. 23744, 23977, 23973 |  | Reuse of ML / FI | Manual | 20 | 2 | NA
[5 empty] | 585 | 24.15 | 0

## Requirement defects
Issue key | Summary
GPS-22115 | GPS-14874 (Requirement clarification for AC09 & PCBR-850)
GPS-21992 | GPAS_PC_GPS-14143_ Requirement Defect_ Version should be 2.0 when language is 'German' and Base country is 'Switzerland' for Cyber products
GPS-21834 | GPS-14133("Not required" should be removed from Tax collection basis)
GPS-21644 | Requirement Defect_Business Policy should display with coinsurance suffix in Billing Center.
GPS-21638 | GPS-14874(Need some clarification on Requirements)
GPS-21590 | Requirement Update_GPS-17712-Appended Event should no longer be considered for ingestion of migrated renewal policies into PolicyCenter.
GPS-21355 | GPAS_PC_GPS-17199_ Requirement Defect_Coinsurance Validations when Duplicate Coinsurer's are added and/or Lead Coinsurer is not added when Beazley's Role = Follow
GPS-21353 | GPAS_PC_GPS-17199_ Requirement Defect_Tax% should not change when Tax amount is overridden
GPS-21114 | Requirement defect_Country 'Netherlands Antilles' should be removed from Policy Address Country dropdown
GPS-20838 | GPAS_PC_ Requirement Defect_ Abbreviated product names (FIPI, IMI, PEPL, POSI) incorrectly displayed in Marketable Product Type list
GPS-20836 | GPAS_PC_ Requirement Defect _‘None’ option incorrectly displayed in US D&O Insurance – Structure Type dropdown list
GPS-20780 | Requirement-defect_ Policy Info – Incorrect Conditions for Primary Named Insured Picker
GPS-19215 | Requirement Defect_GPS-14273-TypeFilter defaults and Broker editability ignoring Policy Change Reason for BIDACProducts
GPS-19011 | Requirement-defect_ Excess Limit not displaying in UI and Attachment Point visibility unclear.
GPS-18817 | Requirement defect_Trading name and Legal name mapping update from CRM to kafka to GWPC
GPS-8339 | GPS-4818_Handling of Broker Changes on Policy Change Backdated to Effective Date – FLS update required
GPS-597 | Change in Requirement - Status & Sensitivity Defaults & impact of Name update
GPS-577 | GPAS_PC_Requirement defect_BZPC-214_“Address Lookup Service isn’t available right now. Please use the Override Address Lookup option or try again later” this warning message needs to dispaly when service unavailable
GPS-22979 | Requirement Defect for Tax Collection Basis should get updated accordingly with change for one Tax Type

## E2E
Total
Test cases | 99
identified during Cyber testing but were common for ML, FI (Incl invoices and Data ) | 71
How many defects reported - Cyber only. | 13

## Regression exec defects
Functionality Type | Defect Number and Status | No. of Defects
A. Product specific changes | GPS-22146 - Closed | 28
GPS-22030 - Closed
| GPS-22064 - Closed |  |  | Total number of defects | 35
| GPS-22150 - Closed |  |  | Common defects b/w ML/FI &Cyber | 4
| GPS-22149 - Closed |  |  | Cyber only defects | 31
GPS-22104 - Closed
GPS-22169 - Closed
GPS-22179 - Closed
GPS-22191 - Closed
GPS-22269 - Closed
GPS-22450 - Closed
GPS-22451 - Closed
GPS-22695 - Closed
GPS-22854 - Closed
GPS-22928 - Closed
GPS-21091 - Closed
GPS-20971 - Closed
GPS-21448 - Closed
GPS-21463 - Closed
GPS-21904 - Closed
GPS-21993 - Closed
GPS-22022 - Closed
GPS-22023 - Closed
GPS-22447 - Closed
GPS-22511 - Closed
GPS-23209 - Closed
GPS-22064 - Closed
GPS-24256 - Closed
B. No changes for Cyber compared to ML/FI | GPS-23411 - Closed | 3 | Cyber only
| GPS-23397 - Closed |  | Cyber only
| GPS-23322 - Closed |  | ML & Cyber
C. Exploratory testing | GPS-23399 - Closed | 2 | Cyber only
| GPS-23353 - Closed |  | ML & Cyber
D. Fixes and CRs (Subset) | GPS-23452 - Closed | 2 | ML & Cyber
| GPS-23363 - Closed |  | ML & Cyber
35