## Sheet1
Issue Category | Description | Tactical fix | Strategic fix | Further action required? | Priority | Action taken
Insight Payload | Broker Contact ID attribute missing | Change implamented in IG App. Code updated to create unapproved broker when attribute is missing. | InSight need to send the attribute in the submission payload | Insight to deploy latest code as in Test instnaces
| Address Line 1 missing for insured- mandatory field | Edit the payload in exception queue/s3 bucket and rerun | Key in this field when creating submission in InSight | Genpact business process
| Period start, Period end - mandatory fields for submission, but not mandatoy in InSight UI, so not always used by Genpact | Edit the payload in exception queue/s3 bucket and rerun | Key in these 2 fields when creating submission in InSight | Genpact business process
ADL | Broker contact ID - Issue 2
| Broker ID | Edit the payload | Not able to locate matching Broker ID but not able to take unapproved broker | This is a defect - Set "isPlaceholder" to true for unapproved broker scenarios (fail as we have ==1 check) |  | Producer code loaded with ADL for unapproved broker
Broker Contacts are not linked to Organizations
Status Of Agreement, Agreement Type, Beazley Entity are missing on Office Organizations
Invoice Generation | Batch scheduler to tigger invoice did not kick off | Manually run | Work with Guidewire | Work with Guidewire
Cleanup | Failed Payloads Record still in exception queue
|  |  |  | Analysis to be carried out | Medium
Query - more than 1 record of submission | Draft submission is getting created though certain failures
Verifications Pending | UW Control - 2nd call for full details |  |  | Analysis to be carried out | High
InSight Clearance | Clearance |  |  |  | Very High
ADL | ADL clean up? |  |  |  |  | Balaji/Ramesh | Vamshi to review
2026-06-11
Submission-1 | Policy period missing- 41f35dda-c984-4323-8133-9cab2162cd90
Submission-2
Submission-3
Submission-4
Submission-5
Submission-6
Submission-7