## Slide 1: Beazley gpas and Billing 2-WEEK SPRINT APPROACH
Draft: Jan 2024

## Slide 2
GPAS & Billing: 2 Week Sprint Approach : Initial View
Area of sprint | 4-week sprint | 2-week sprint
Sprint Days | 20 | 10
User story size (story points) | 5, 8 or 13 | 3 or 5
User story test execution | Begins approx. 8th day or after | Begins as early as 3rd or 4th day
User story demos & sign-off | Begins approx. 11th day onwards | Begin as early as 4th and 5th day
Demo Sign-off | Is between 1-3 days | Must be the same day
Business Elaborations | N-1 sprint | N-2 sprint
User story handovers | N sprint | N-1 sprint
What becomes critical:
Product owners & Business SME availability required on all days of the sprint both for elaboration & development weeks
Turn around times required the same day or day+1
  story sign-off in elaboration
  query resolution
  story sign-off post development
  architecture and design decisions
Strict & Absolute Definition of Ready & Definition of Done compliance for stories part of each sprint
No changes to be made in the story during development weeks
Dependencies delivered and resolution must be achieved in N-1 sprint
Other areas of change to be considered:
A master planning session is required every 8 weeks
Orientation session required to teams within GPAS & Billing on new ways of working
Sprint planning and outputs – documented and agreed in JIRA
Review & alignment of team capacities
Sprint closure reporting and sign-off process to be optimized
Review frequency for more regular governance forums such as architecture, business & leadership
Transitioning from a 4-week Sprint to 2-week Sprint construct requires a mindset change to be more Agile, more Responsive and more Flexible as a team, to achieve its purpose and alignment to the Programme objectives
Specifics of what will be different

## Slide 3
GPAS & Billing: 2 Week Sprint Approach : Initial View
RISK | Mitigation
RISK ID – GPAS060 Unable to secure Product Owners and Business SME availability in the new approach leading to loss of efficiencies for core development teams thereby impacting the release plan | Secure the existing POs dedicated to the programme and gain agreement that SME time is prioritised onto GPAS and Billing when it is required. Align PO/SME resource to 9-5pm UK working hours. Agree delegated sign-off where PO unavailable to avoid single point of failure and delays. Team to continue to provide forewarning on demos, US reviews, sign offs etc.
RISK ID – GPAS068 Complex Integration stories cannot be completed in smaller US numbers of 5 story points | Have separate development & test user stories Create multiple parts to a single integration story if required Integration will be showcased when all components of dev and test are complete.
RISK ID – GPAS049 Dependencies not delivered to expected timeline, which will lead to significant delays and not achieving sprint goals | Consider bringing later scope forward where possible (opportunities will be limited and focus best placed on securing dependencies on time).
RISK ID – GPAS069 Completion of elaborations in N-2 sprint is a change to the current ways of working and has a risk of not fitting into the new approach, however, compromising on this will impact our velocity and efficiency. | Introduce a checkpoint between N-2 and N-1 to ensure all still valid and correct. Actions to be updated and closed in 24 hours.
Note: Failure to follow the approach outlined and mitigate risks will lead to a reduced payload and potentially adversely impact the efficiencies sought from moving to 2-week sprints.