## Slide 1: Beazley gpas and Billing OPERATING MODEL
Drafted: Mar-2024
Ways of Working for GPAS Programme Delivery – DRAFT v0.1

## Slide 2
S.No | Version | Month/Date | Changes made
1. | 0.1 | March-2024 | First version of Ways of working, focused more at Inception phase method & processes
2 | 0.2 | 17th March 2024 | Updates made basis feedback received from Warren – changes made to Team structure Warren to come back on Sign-off names from Beazley for Inception deliverables
3 | 0.3 | 19th March 2024 | Updates to Core team based on Beazley feedback, text changes on context slide, Removed names against responsibilities for Beazley, Added GPAS and Billing in the RACI, New integration entry in RACI, Removed the approvers and sign-off to be updated later once Beazley confirms
4 | 0.4 | 25th March 2024 | Updates to RACI, Two in a Box Structure and other minor changes
  Document change history

## Slide 3: CONTEXT
Ways of working is a Capgemini recommended way of Program execution allowing all relevant parties and stakeholders to operate and collaborate towards achieving the common program goals. This document intends to target both processes and behaviours that form the building blocks of successful completion of GPAS
This Ways of working is specifically designed for GPAS and Billing scope of work only and for the scope of work owned by Capgemini. The processes, behaviours and recommendations outlined here may not be applicable outside GPAS to the wider Modernization program
The Ways of working document is expected to evolve iteratively, through Inception phase before it can be made final. However, throughout the GPAS program execution, the delivery method or process may undergo change in certain sections if all the influenced parties agree there is a need for improvement

## Slide 4: Ways of working
Scope of Inception phase
Key Success factors
Inception activities – week wise split
Workshops – rules of engagement
Inception phase deliverables
Team Structure for Inception
Design Principles
RACI
Key roles – Beazley and Capgemini
Governance – Key roles, Cadence, Escalation, Change Control
Tools for Inception
JIRA set-up and governance
To be built & agreed in parallel to Inception for start of build
  Foundation & Waves Construct
  Backlog management process
  Sprint construct
  Cadence and ceremonies
  User story management
  Activities list
  DoD and DoR - Definition of Done and Definition of Ready
  Third party alignments and SLA
  Metrics & Reporting
  Collaboration and Tool sets
INCEPTION PHASE
BUILD PHASE
The immediate focus is to draft and agree on Ways of working applicable for the start of Inception phase covering activities, deliverables, methods and processes expected to be jointly built and done by Capgemini and Beazley. As a next step, this document will be extended to document methods and processes applicable to the Build phase.
To be built & agreed for start of Inception

## Slide 5: Programme Inception phase helps create the foundation & vision of the Transformation
Foundation Release Mobilization is focused on enabling MVP Design and Build to start
Build the foundation with core principles intact. – data/ automation / experience
Collaborative pre-work on entry criteria to ensure rapid start and timely completion
Transform the plan from the Inception to reality, transforming the business requirements to functional systems
Plan for future Releases and LOB
Confirm Roll-out Approach
Key Design Decisions log
Programme Inception
Design and Build
Programme Inception is focused on “Designing the next winning proposition”
A common 12-weeks Programme Inception phase to clarify and align the scope in all Products for a Foundation, followed by the implementation of the planned Releases.
What you’ll get:
Prioritized backlog
High Level Design
Foundation release plan
Key risks & assumptions
Dependencies detailed

## Slide 6: KEY SUCCESS FACTORS
Right Time
  Multi-day sessions
  Aligned workshops
  Covering India, UK and US time zone
Right Inputs
  Product / Process Design
  OOTB Guidewire Process Flows
  Interfaces
Right Enablers
  Guidewire Instance
  Collab Tools
  Reliable access to VDIs
Inception Phase Principles
OOTB Conformance
Business Priority / Rationale
Design for Future
Outputs more focused at Foundation release
GPAS Ways of working
Prioritized Backlog
Effort & Resourcing
GPAS & Billing HLD and Delivery Plan
Key Design Decisions
Migration Strategy
Integration Inventory
Dependency tracker
Test Strategy
Rationalized Product set
Pebbles / Rocks / Boulders
Categorizing elements of solution for appropriate escalation to finalise scope
Right Team
  Product Owners, Business SME
  Right Capgemini team
  Collaboration is key
Right Decisions
  Timely & accurate decisions
  On time escalations for help
  Lean thinking
AGILE
MATURITY
COLLABORATION
DEPENDENCIES MANAGEMENT

## Slide 7: INCEPTION PLAN – By WEEK BREAKDOWN
Workshops - Tuesday, Wednesday, Thursday
(AM: 10-12:30
PM-13:30-17:00)
The Inception plan will be shared separately for Beazley’s review and preparation for start

## Slide 8
Rules of Engagement
  All meeting and workshop invites to include:
    Purpose of the meeting / Agenda
    Input to the meeting
    Expected output from the meeting
    Deliverable(s) output (as required)
  Be straight and transparent
  Business attendees and availability to be confirmed by Beazley (Senior Product Owner/relevant Product Owner) before invitation is sent
  Parking lots/Decision logs to be captured and logged in the required trackers
  Critical decisions to go through appropriate Programme Governance forums and documentation
  On site and remote attendance options to be available
  Recording of sessions to be used where appropriate
  All sessions to be aligned to overall programme strategy
  All material to be utilised for Beazley programme purposes only
Guidelines for meetings and workshops
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 9: Inception programme deliverable outputs
Functional Activities
Obtain an understanding of in scope functional areas
Obtain and understanding of as is current processes
Receive demos of current systems
Review the existing capability map and identify any gaps
Deliverables at programme level & expected signatories
Deliverable Names | High level Description and Expectation | Review | Sign Off
PD1: GPAS Ways of Working | Detailed methodology, Governance model, Change control model, communication management, Reporting & meeting cadence, Initial team structure, RACI, Escalation approach, Tools for build & usage boundaries | TBD | TBD
PD2: Prioritized Backlog (Foundation) | Documentation of Foundation Release Functional requirements, in scope Epics/Features. User Stories scope statement defined in excel format for uploading into JIRA | TBD | TBD
PD3: Resourcing & Efforts (Foundation) | Breakdown of resourcing needs (by quarter) aligned to effort and bottom-up estimation of Epics and Features against the delivery plan. High level scope, budget, and resourcing/effort should reconcile. | TBD | TBD
PD4: Delivery Structure & Plan (Foundation) | Phase & Workstream definitions, objectives and milestones. Verification and Acceptance. Plan detailing the Guidewire sprint plan, number of sprints, dates, and high-level proposed scope breakdown. | TBD | TBD
PD5: GPAS High Level Design | Aligned to agreed architecture decisions and principles Detail how Policy and Billing Center will fit into Beazley ecosystem. Detail the key Integrations for the Foundation release | TBD | TBD
PD6: Migration Strategy | Approach to migration in terms of execution and timing. High-level data requirements at an entity level, from relevant business areas. | TBD | TBD
PD7: Integration Manifest | Inventory of integrations defining cardinality, service contract ownership, integration pattern or method, initial view on complexity. Definition of any intermediated services or gateways to influence design. | TBD | TBD
Deliverables to be produced during Inception, ready for review and response feedback loop. All deliverables to have a wider review distribution which will be confirmed on the deliverable itself.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 10: Inception programme deliverable outputs
Functional Activities
Obtain an understanding of in scope functional areas
Obtain and understanding of as is current processes
Receive demos of current systems
Review the existing capability map and identify any gaps
Deliverables at programme level & expected signatories
Deliverables to be produced during Inception, ready for review and response feedback loop. All deliverables to have a wider review distribution which will be confirmed on the deliverable itself
Deliverable Names | High level Description and Expectation | Reviewer | Sign Off
PD8: Detailed Dependency Tracker | Internal and External Dependencies detailed with dates and deliverables agreed with each of the related parties. | TBD | TBD
PD9: Functional & Technical Principals | Functional and Technical Design principles documented. | TBD | TBD
PD10: GPAS Test Strategy | High level scope of key test phases, gates and entry/exit criteria; view of resourcing. Input into Definition of Done (DoD) including acceptance criteria, automation definition. Definition of the GPAS environment requirements and when they will be required by to meet the timelines. | TBD | TBD
PD11: Product Set | Rationalised product set for foundation release Identification of any products requiring further analysis and key decision papers where necessary. | TBD | TBD
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 11: Teams for inception and Beyond…
Architects
Technical Leads
Delivery Leads
Product Owner
Test Manager
Brett Fabian-Smith
Vamshi Chennamadhavuni
(Guidewire)
SivaramaKrishna Narayanan
Athik Miah
(Billing)
Dean Johnston
(Enterprise Architect)
TBD (from Hexaware)
Stephen Payne
Matt Reynolds
(Business Architect)
Gourab Marik
(Integration)
Balaji KV
(Billing)
Programme Directors
Max Cartwright
Warren Pilkington
Ananda Arasu Ponnaiah
(UK)
Natraj Gudla
(India)
Product Rationalization
Business Sponsors / Delivery Exec
Vanesssa Ortega
Procurement
Ian Craney
Ben Lowles
Abby Vredenburg
(Business Process)
Beazley
Capgemini
Barry Houston
Akhlas Hafiz
Functional Leads
Sherezad Contractor
(Policy)
Sriram Jagannathan
(Billing)
Peter Dixon
Kelly Reisling
Jeff Colandrea
Rajesh Bandaru
(Policy)
Current Platform Owners
Jeff Colandrea
(Beazley Pro)
Devin Wells
TBD
(Policy)
Patrycja Kuligowska
(Billing)
Devin Wells
(Policy)
Kerstin Kasdorf
(Process excellence)
Steve Flood
(Claims)
Subject Matter Experts
Jigar Solanki
Dev Ops
TBD
TBD
Matt Reynolds
Troy Baillargeon
Steve Enness
U/W SMEs..TBD
Mark Parlsey
Migration
Andy Ford (BA)
Anita Param (BA)
Dauda Jammeh
Saad Jassani
(Process Excellence)
Subu Ramasundaram
(Process Excellence)
Molly Spolarich
(Operations)
Carol Hamilton
(Billing)
Alejandro Gonzalvez Suarez
(Billing)
Sarah Carroll
(Billing)
Jonathan Abbott
(Billing)
Danny Sohal
(Finance EA)
Marta Latuszek
(Finance Business Architect)
Dominik Dyszkowski
(Billing)
Antonio Seager
(Finance)
Notes: Platform owners – Jeff owns Beazley Pro and reports into IT

## Slide 12: Teams for inception and Beyond…
Architects
Technical Leads
Delivery Leads
Product Owner
Test Manager
Brett Fabian-Smith
Vamshi Chennamadhavuni
(Guidewire)
SivaramaKrishna Narayanan
Athik Miah
(Billing)
Dean Johnston
TBD (from Hexaware)
Stephen Payne
Matt Reynolds
Gourab Marik
(Integration)
Balaji KV
(Billing)
Programme Directors
Max Cartwright
Warren Pilkington
Ananda Arasu Ponnaiah
Natraj Gudla
Product Rationalization
Business Sponsors / Delivery Exec
Vanesssa Ortega
Procurement
Ian Craney
Ben Lowles
Abby Vredenburg
(Business Process)
Beazley
Capgemini
Barry Houston
Akhlas Hafiz
Functional Leads
Sherezad Contractor
(Policy)
Sriram Jagannathan
(Billing)
Peter Dixon
Kelly Reisling
Jeff Colandrea
Rajesh Bandaru
(Policy)
Current Platform Owners
Jeff Colandrea
Devin Wells
TBD
(Policy)
Patrycja Kuligowska
(Billing)
Devin Wells
(Policy)
Kerstin Kasdorf
(Process excellence)
Steve Flood
(Claims)
Subject Matter Experts
Jigar Solanki
Dev Ops
TBD
TBD
Matt Reynolds
Troy Baillargeon
Steve Enness
U/W SMEs..TBD
Mark Parlsey
Migration
Andy Ford (BA)
Anita Param (BA)
Dauda Jammeh
Saad Jassani
(Process Excellence)
Subu Ramasundaram
(Process Excellence)
Molly Spolarich
(Operations)
Notes: Platform owners – Jeff owns Beazley Pro and reports into IT

## Slide 13
Key Cross-Programme Delivery Support
GPAS & BILLING – DRAFT STRUCTURE v0.2
Modernisation Steering Group
See previous Slide)
Risk Board
(see previous slide)
Delivery Teams (see over)
Key:
Beazley
Capgemini
Guidewire
US Based
India Based
Canada Based
TBD – Cap/Beazley/GW
Other Programme Stakeholders
Warren Pilkington (Prog Director)
Max Cartwright
(Prog Director)
Athik Miah
(Del Lead - Billing)
Ananda A Ponnaiah
(Del Lead UK)
Dean Johnston
(Ent Architecture)
Brett Fabian-Smith
(Ent Architect)
Stephen Payne
(Del Lead – GPAS & Billing)
Program Leadership
Danny Sohal
(Finance Architect)
TBD
(Lead GPAS PO)
TBD
(Functional Lead)
Owen Humphries
(Technical Lead)
TBD
(Lead Finance PO)
TBD
(GW Ent Architect)
Frederic Brunner
(Delivery Director)
Jeff Colandrea
(Platform Owner)
Natraj Gudla
(Del lead – India)
Barry Houston
(Delivery Exec)
Ben Lowles
(Procurement Lead)
Ian Craney
(Procurement Lead)
Akhlas Hafiz
(Head of Modernisation)
Dauda Jammeh
(Bus Owner - Finance)
Executive Leadership
Stephan Benet-Weiler / Aine Kane (Del Exec)
Vanessa Ortega (Business Owner)
Kerstin Kasdorf
(Policy PO)
Sherezad Contractor
(PC Func Ld)
Rajesh Bandaru
(PC Tech Ld)
Patrycja Kuligowska
(Billing PO)
Sriram Jagannathan
(BC Func Ld)
Balaji KV
(BC Technical Lead)
Gourab Marikm
(GW Int. Lead)
Vamshi C
(Guidewire Lead)
TBD
(Policy Mig’n Lead)
POs, Functional & Technical Leads
TBD (Hexaware)
(Test Mgr)
SivaramaKrishna Narayanan
(Test Manager)
TBD
(Integration Lead)
TBD
(Migration Lead)
TBD
(GW PC Lead)
TBD
(GW BC Lead)
TBD
(GW Int Lead)
TBD (Training / Bus Readiness Lead)
TBD
(Data Lead)
TBD
(Docs Lead)
Kerstin Kasdorf
(Process SME)
Saad Jassani
(Process SME)
Subu Ramasundaram
(Process SME)
Abby
Vredenburg
(Bus Proc PO)
Process Excellence
Andy Ford
(Migration BA)
Anita Param
(Migration BA)
Dominik Dyszkowski
(BA)
Alejandro Gonzalvez Suarez (BA)
TBD
(Prod Rationaln BA)
TBD
(Process Design BA)
Business Analysis
Devin Wells
(TBD)
Mark Parlsey
(TBD)
Jeff Colandrea
(BeazleyPro)
Antonia Seager
(Finance)
Current Plat. Owners
Jigar Solanki
(Solution Architect)
TBD (GW Assurance Architect)
TBD
(Solution Architect)
Marta Latuszek
(Fin Architect)
Matt Reynolds
(Bus Arch)
Architects
Shared Services SMEs
TBD
(IT Security)
TBD
(Risk)
TBD
(Audit)
TBD
(Compliance)
PAS BAU transition (based on ITOM/BAU Serv Mgmnt Structure)
Simon Fry
(Infrastructure)
TBD
(DevOps)
Infra / DevOps
TBD
(DevOps)
Devin Wells
(Policy SME)
Steve Flood
(Claims SME)
Molly Spolarich
(Operations SME)
Troy Baillargeon (Prod Rationalisation)
Steve Enness
(Prod Rationalisation)
Carol Hamilton
(Credit Control NA)
SMEs
Sarah Carrol
(Billing)
Jonathan Abbott
(Billing)
Peter Dixon
(Prod Rationalisation)
Kelly Reisling
(Prod Rationalisation)
TBD
(Prod Rationalis’n BA)
TBD
(Prod Rationalis’n BA)
Devin Wells
(Policy SME)
Matt Reynolds
(Bus. Architecture)
Steve Flood
(Claims SME)
Troy Baillargeon (Prod Rationalisation)
Jeff Colandrea
(Platform Owner)
Abby
Vredenburg
(Bus Proc PO)
TBD
(Data Team Reps)
Product Rationalis-ation
TBD
(UW SMEs)

## Slide 14
Key:
Beazley
Capgemini
Executive Leadership
Program Leadership
Delivery Teams
Foundation Release
(High Level)
POs, Functional & Technical Leads
Business Analysts
Product Owner
Business SMEs
Developers
GW Consultants
Business Analyst
Tech Lead
Developers
Testers
Testing Lead
Policy Lead
Product Owner
Business SMEs
Business Analysts
Scrum Master
Dev Lead
Developers
GW Consultants
Business Analyst
Tech Lead
Developers
Testers
UK
India
Billing Lead
Integration Lead
Technical SMEs
Developers
GW Consultants
Business / Mapping Analyst
Tech Lead
Developers
Testers
Automation Testers
Product Owner
Business SMEs
Technical SMEs
Business / Migration Analyst
Migration Developers
Testers
Migration Lead
UAT Testers
SIT Testers
Combined Teams
Guidewire
Product Rationalis-ation
Process Excellence
Infra / DevOps
Business Analysis
SMEs
Current Plat. Owners
Architects
Shared Services
Product Owner
Business SMEs
Technical SMEs
Business / Data Analyst
Data Developers
Testers
Data Lead
Training & Business Readiness
Business Readiness Lead
Training and Communication Lead
Model Office Lead
Docs Lead
Product Owner
Business SMEs
Technical SMEs
Business / Docs Analyst
Docs Developers
Testers
GPAS & BILLING – DRAFT STRUCTURE (+DEVELOPMENT) v0.2

## Slide 15: Design principles
support the agreed Release scope?
ensure the business is not in a worse position from before?
support a move off existing systems
support flexibility and maintainability for future releases?
All key decisions to move through formal programme governance decision bodies
abide by the Beazley architectural principles?
Does the decision:
allow for scalability and is not closed off for future-states
Decision making process:
Workshop/Meeting where key question arises
Identification of key decision needed, decision owner and required inputs to enable decision
Creation of key decision paper and supporting material(s)
Presentation at BDA/TDA or both as required
BDA/TDA decision output documented and stored
Ratification of BDA/TDA decision output at Programme Leadership/Steering if required
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 16: KEY AREAS – raci [1]
A | Accountable | Authority and decision making
R | Responsible | Responsible for actualisation of the task
C | Consulted | Engaged stakeholder, consulted in decisions, delivery and approach to enable their input
I | Informed | Informed stakeholder receiving updates and outputs only
Area |  | Beazley |  | Capg |  | Guidewire
Modernization Program Activities |  | A |  | C |  | I
Program planning & delivery |  |  |  |  |  | 
Ways of working for all Programs under Modernization |  |  |  |  |  | 
Procurement Management |  |  |  |  |  | 
Program communications and stakeholder management |  |  |  |  |  | 
SteerCo & Leadership reporting |  |  |  |  |  | 
PMO |  | A |  | C |  | I
Risk and Issue Management tracking |  |  |  |  |  | 
Dependency Mangement tracking |  |  |  |  |  | 
Programme Metrics & Milestone tracking |  |  |  |  |  | 
Programme Budget & Invoicing payments tracking |  |  |  |  |  | 
Project infra needs set up coordination & tracking |  |  |  |  |  | 
Deliverables tracking |  |  |  |  |  | 
Requirements Gathering and Management (GPAS & Billing) |  | A |  | R |  | C
Product Backlog refinement and Business process mapping |  |  |  |  |  | 
User story refinement with business rules and acceptance criteria |  |  |  |  |  | 
Requirements sign-off |  |  |  |  |  | 
Prototyping and mock-ups |  |  |  |  |  | 
Workshops schedule, execution & follow-up |  |  |  |  |  | 
Architecture and Technical Management (GPAS and Billing) |  | A/R |  | R |  | R
Confirm Architecture and Design Principles |  |  |  |  |  | 
High level designs |  |  |  |  |  | 
Create and maintain Technical Design Decisions |  |  |  |  |  | 
Low level design |  |  |  |  |  | 
Data Migration Strategy |  |  |  |  |  | 
Environments and Infrastructure |  | A/R |  | C |  | R
Infrastructure and environments planning and provisioning |  |  |  |  |  | 
Deployments, maintainence and supplier issues resolution |  |  |  |  |  | 
Capacity planning & scalability |  |  |  |  |  | 
Security and Compliance implementation |  |  |  |  |  | 
Monitoring, management & performance optimisation |  |  |  |  |  | 
Area |  | Beazley |  | Capg |  | Guidewire
GPAS and Billing Delivery |  | C |  | A/R |  | C
Develop user stories adhering to Guidewire Cloud standards |  |  |  |  |  | 
Unit testing adhering to Guidewire Cloud Standards |  |  |  |  |  | 
Sprint plan and raising dependencies |  |  |  |  |  | 
Resolve Guidewire Cloud standard assessment observations |  |  |  |  |  | 
Sprint progress reporting |  |  |  |  |  | 
E2E Testing |  | A/R |  | C |  | I
End to End Test Strategy and Execution |  |  |  |  |  | 
JIRA and Confluence set-up |  |  |  |  |  | 
Metrics and Reporting |  |  |  |  |  | 
Risks and Issues management |  |  |  |  |  | 
Defects resolution specific to GPAS & Billing components |  | C |  | A/R |  | C
GPAS and Billing Functional Testing |  | A |  | R |  | I
Functional test plan and execution |  |  |  |  |  | 
Risks, Issues and Dependencies status reporting |  |  |  |  |  | 
Metrics and Reporting using JIRA |  |  |  |  |  | 
Release Management |  | A |  | C |  | C
End to end release plan roadmap for the Program |  |  |  |  |  | 
Strategy, Processes and teams for deployments, check points |  |  |  |  |  | 
Third party coordination for all environments |  |  |  |  |  | 
Cutover, Go-live and Post Go-live Support |  | A/R |  | R |  | R
Cut-over plan and Implementation Management |  |  |  |  |  | 
Establish post Go-live Support Model |  |  |  |  |  | 
Infrastructure and environments set-up |  |  |  |  |  | 
Service Design and PGLS Plan |  |  |  |  |  | 
Incident fixes specific to GPAS & Billing during warranty |  | C |  | A/R |  | C
Key
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 17: KEY AREAS – raci [2]
A | Accountable | Authority and decision making
R | Responsible | Responsible for actualisation of the task
C | Consulted | Engaged stakeholder, consulted in decisions, delivery and approach to enable their input
I | Informed | Informed stakeholder receiving updates and outputs only
Key
Area |  | Beazley |  | Capg |  | Guidewire
Business Change Management |  | A |  | C |  | I
Change Impact assessment and readiness |  |  |  |  |  | 
Business roll-out plan |  |  |  |  |  | 
Communications and reporting |  |  |  |  |  | 
Legacy |  | A/R |  | C |  | I
Management of legacy party stakeholders |  |  |  |  |  | 
Delivery of dependencies as per Program plan |  |  |  |  |  | 
Management of design, build and testing required by GPAS & Billing |  |  |  |  |  | 
Communication on Legacy changes that impact GPAS & Billing |  |  |  |  |  | 
Status updates and reporting |  |  |  |  |  | 
Finance (Subledger) |  | A/R |  | C |  | I
Management of Finance party stakeholders |  |  |  |  |  | 
Delivery of dependencies as per Program plan |  |  |  |  |  | 
Management of design, build and testing required by GPAS & Billing |  |  |  |  |  | 
Communication on Finance changes that impact GPAS & Billing |  |  |  |  |  | 
Status updates and reporting |  |  |  |  |  | 
Documents |  | A/R |  | C |  | I
Document supplier and platform management |  |  |  |  |  | 
Deliver Document platform dependencies as per Program plan |  |  |  |  |  | 
Documents design |  |  |  |  |  | 
Document template requirements, build and test |  |  |  |  |  | 
Environment and Infrastructure management |  |  |  |  |  | 
Data & Analytics |  | A/R |  | I |  | I
Data Management Strategy |  |  |  |  |  | 
Data & Analytics build and test |  |  |  |  |  | 
Analytics Reporting requirements & build |  |  |  |  |  | 
Dependency management with rest of the Program |  |  |  |  |  | 
CDA |  |  |  |  |  | 
Area |  | Beazley |  | Capg |  | Guidewire
Third Parties (Integrations & Guidewire) |  | A/R |  | C |  | I
Third party management |  |  |  |  |  | 
Third party deliverables alignment to Program plan |  |  |  |  |  | 
Third party environments management |  |  |  |  |  | 
Issues resolution with Third parties |  |  |  |  |  | 
Status updates and reporting |  |  |  |  |  | 
Policy Data Migration |  |  |  |  |  | 
E2E Oversight |  | A/R |  | C |  | I
Legacy Data management |  |  |  |  |  | 
Data Migration Strategy |  |  |  | R |  | 
Data Profiling with production data |  |  |  |  |  | 
Data Migration technical solution |  |  |  |  |  | 
Data Migration mapping and gap analysis |  |  |  |  |  | 
Data Migration implementation and Go-live strategy |  |  |  |  |  | 
UWWB (Underwriting Work Bench) |  | A |  | C |  | I
Requirements management |  |  |  |  |  | 
Deliverables alignment to Program plan |  |  |  |  |  | 
Environments management |  |  |  |  |  | 
Issues resolution impacting Program |  |  |  |  |  | 
Status updates and reporting |  |  |  |  |  | 
GPAS and Billing Integration - External (third party) and Internal (Beazley systems) |  | A/R |  | R |  | I
Integrations design |  |  |  |  |  | 
Integrations inventory |  |  |  |  |  | 
High Level Design |  |  |  |  |  | 
Low Level Design |  |  |  |  |  | 
Technical mapping document |  |  |  |  |  | 
Plan, Build and unit test integrations |  |  |  |  |  | 
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 18: KEY ROLES – Beazley
Role | Named Resource | Responsibilities
Business Owner/ Sponsor |  | Approve scope, target design and execution plans for the PAS iniaitive. Accountable for delivery against OKRs, business outcomes and benefit realisation. Commits or helps facilitate appropriate resources (e.g. SMEs) and support issue resolution for the PAS initiative. Approve and oversee key initiative decisions as adviser Steer solution design and build based on business needs
PAS Delivery Lead |  | Develop the initiative objectives, scope, highlevel implementation roadmap, resource requirements and investment estimates. Working with the delivery partners, create and manage the PAS delivery plans. Manage the delivery teams inc. resource management, supply & demand, technical capability and skills Manage inbound and outbound dependencies needed for the delivery of the component Management of risks and issues impacting progress Responsible for status reporting of the project
Global PAS Product / Platform Lead |  | Helps define the PAS Product Strategy, Vision and Roadmaps alongside the Product Owners in the PAS initiative. Managing and prioritising the PAS Portfolio Backlog taking care to ensure alignment with business architecture, data teams and existing BAU environments. Delivering Value by ensuring the PAS solutions are complete from the user perspective (including operations, change etc) and deliver meaningful business value. Point of escalation and coaching for squad-level Product Owners.
Solution Architect Lead |  | Work with squads to define target technical solutions. Gain approval through Design Authority for technical solutions. Monitor technical risk and mitigation control. Define technical guardrails for delivery squads. Embed technical work into backlogs of delivery squads.
Product Owner |  | There will be different Product Leads depending on the release/wave of PAS implementation. For example, Cyber and D&O in Foundation release. Understand and be able to describe the end-to-end solution in a high level, the use cases and related business drivers. Attend decision making sessions, feeding input regarding the product and its interaction with other components, acting as a point of reference for the product required features and behaviour. Understand business demands and requirements and translate these into solutions that are refined iteratively and present them to the team. Prioritise requirements of the product and make adjustments as needed after each release. Define the future goal of the product (the ‘product vision’) Maintain and own the product backlog. Accepting or rejecting suggested improvements. Report progress, involvement in governance arrangements.
Scrum Master |  | Responsible for the effective and consistent operational performance for the scrum process. Responsible for both timely and effective tracking and reporting on team progress against goals. Responsible for managing team capacity, utilisation and velocity. Responsible for providing Delivery Lead and Product Owners with relevant input for each team member to support each team member’s development and performance needs.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 19: KEY ROLES – Beazley
Role | Named Resource | Responsibilities
Quality Assurance Testing Lead |  | Ultimately accountable for the quality of the overall end to end solution Provides overall QA oversight for test design and execution, striving for commonality where appropriate Accountable for defining Program level test strategies and approaches for all test phases Accountable for planning and oversight of all test phases, including UAT Provides testing oversight and direction, drives execution of testing strategies and manages testing related objectives and issues across the Program
Release Train Engineer/ Manager |  | Partnering with Product Manager Assisting in management of risks, issues and any potential roadblocks Responsible for resolving contingencies and complicated issues, provide leadership to project teams, and act as a consultant/coach to management Responsible for DevOps and improvement of workflow
Business Architecture Lead |  | Accountable for developing the business architecture strategy Applying structured business architecture approach and methodology Drives and facilitates the right discussions with business leaders to identify business capabilities in relation to current and future business objectives Responsible for presenting recommendations and solutions clearly and concisely Accountable for a specific LOB, business pillar or multiple segments, and high level of complexity and attributes
Change Management Lead |  | Responsible for managing all types of change Evaluates the impact of change Supports development of communications relevant to change initiatives Accountable for defining success metrics and measuring performance against these
Training / Communication |  | Coordinating the development, execution, refinement, and measuring the impact of programme outreach, communications, and knowledge management strategies Responsible for coordinating development of training / learning materials Accountable for the organisation, coordination of workshops and events Responsible for supporting communications, knowledge management, and training activities
Delivery Partners (Third party suppliers to Beazley) |  | Partner with the Senior Delivery Lead Manage the scope of services in support of delivering the PAS initiative Manage the deliverables to be produced in support of delivering the PAS initiative Manage any CRs related to the component and services being provided in support of delivering the PAS initiative Create and manage the plans for the delivery of the services in support of the PAS initiative Manage the delivery squads inc. resource management, supply & demand, technical capability and skills Jointly manage sprint planning, retrospectives and reporting relating to services being provided in support of delivering the PAS initiative Manage inbound and outbound dependencies needed for the delivery of the component Coordinate activities and schedule across the PAS initiative Management of risks and issues impacting progress
Delivery Squads (Beazley SME and/or Third party suppliers to Beazley) |  | End-to-end delivery of each product Provide requested SME input into tasks, activities, decisions Flag risks and issues to the Senior Delivery Lead and/or Delivery Partner Proactive updating of Jira, the backlog and the sprint boards in conjunction with the scrum master
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 20: KEY ROLES - capgemini
Role | Named resource | Description | 
Delivery Executive | Barry Houston | Responsible for overall Services quality and delivery Assist in the resolution of issues and change controls | Prepare for and support Steering/Policy Executive Advisory Group Meetings Monitor program progress
Program Director | Max Catwright | Responsible for in-scope Program activities Provide Program status reporting on a regular basis to Beazley Program and Executive Leadership | Responsible for overall Services quality and delivery of the Program Responsible for day-to-day management and tracking of the in-scope Program activities
Engagement Manager | Ananda Arasu Pommaiah | Manage the detailed Program plan in collaboration with Beazley Leadership Team Provide Program Status reporting on a regular basis to Beazley Program Leadership | Facilitate Decisions, Issues and Risk management across the core program and escalate to Beazley in advance of the materialization of potential risks and issues that may delay the program. Assist the resolution of issues and change controls
India Delivery Executive | Natraj Gudla | Manage the detailed Program plan in collaboration with Beazley Leadership Team Provide Program Status reporting on a regular basis to Beazley Program Leadership | Facilitate Decisions, Issues and Risk management across the core program and escalate to Beazley in advance of the materialization of potential risks and issues that may delay the program. Assist the resolution of issues and change controls
Product Rationalisation | Peter Dixon Kelly Riesling | Provide subject matter specialist advice with regard to overall business requirements and product backlog Provide input on solving business problems within the defined application landscape by working with the business and Technical resources. | Coordinate with Functional Lead and Technical architect to help define implementation scope of work.
Enterprise Architect | Brett Fabian-Smith | Provide leadership and architectural expertise across a broad set of technologies, including integration & middleware technologies Consult with and advise the Program team on technology and strategic decisions | Identify architectural constraints for the architectural level (project, domain, application) based on technical and organizational requirements Provide subject matter specialist advice with regard to overall solution architecture and technology
PolicyCenter Functional Lead | Sherezad Contractor | Provide Policy subject matter experience Work with Beazley business leadership to drive overall business requirements | Provide leadership and direction for elaboration and RSWs Provide joint review and approval of deliverables
BillingCenter Functional Lead | Sriram Jagannathan | Provide Billing subject matter experience Work with Beazley business leadership to drive overall business requirements Provide leadership and direction for elaboration and RSWs | Provide joint review and approval of deliverables Lead with the high-level implementation approach for complex functional requirements
PolicyCenter Technical Lead | Vamshi Chennamadhuveni | Provide subject matter specialist advice with regard to GW PC Conduct configuration option analysis to support business requirements Provide input on GW PC best practices, constraints, and effort during workshops, including pre-work | Provide input on effort and impact associated with potential configurations/customizations Support the Policy Functional Lead with the high-level implementation approach for complex functional requirements
BillingCenter Technical Lead | Sriram Jagannathan | Provide subject matter specialist advice with regard to GW BC Conduct configuration option analysis to support business requirements Provide input on GW PC best practices, constraints, and effort during workshops, including pre-work | Provide input on effort and impact associated with potential configurations/customizations Support the Policy
Integration Lead | Saharsh Gupta Gourab Marik | Provide integration and technical architecture guidance for GW Lead analysis effort of interface specification documents | Lead the integration design effort for specified integration points Provide direction and technical guidance
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 21: KEY ROLES - guidewire
Role | Named resource | Description
PolicyCenter Principal Architect | TBD | PolicyCenter technical architect
PolicyCenter Principal Business Analyst | TBD | PolicyCenter functional and product expert
BillingCenter Principal Architect | TBD | BillingCenter architect
Integration Principal Architect | TBD | Guidewire Integration architect
London Market Specialist | TBD | Guidewire London Market and product architect
Guidewire Delivery Management (non-billable part time role) | TBD | Guidewire point of contact for the implementation and Guidewire assigned resourcing.
Guidewire Product (non-billable part time role) | TBD | Guidewire London Market expert and point of liaison with Guidewire product team. Needs to understand the business needs so that any future Guidewire product related enhancements can be planned.
Guidewire Product (non-billable part time role) | TBD | Guidewire London Market expert and point of liaison with Guidewire product team. Needs to understand the business needs so that any future Guidewire product related enhancements can be planned.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 22: governance
The overall success of this engagement will be based on close collaboration between all parties, transparency and fact-based decision making. We will also use this Governance process to keep us all collectively honest and true to the Programme objectives.
Daily
Weekly
Monthly/Quarterly
Weekly
Sponsor Review
Change Control Board
Dependency Review Forum
Technical Design Authority
Business Design Authority
RAID Review
Agile – Daily Stand-up / Scrum of Scrums
GPAS Programme Management Update
Decisions
Decisions
Reporting
Reporting
Procurement Update
SteerCo
Leadership Update
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 23
Proposed Programme CADENCE
Friday
9.00 – 9.30 |  |  |  |  | 
10.00 – 10.45 |  |  |  |  | 
11.00 – 12.00 |  |  |  |  | 
12.00 – 13.00 |  |  |  |  | 
13.00 – 14.00 |  |  |  |  | 
14.00 – 15.00 |  |  |  |  | 
15.00 – 16.00 |  |  |  |  | 
16.00 – 17.00 |  |  |  |  | 
Daily Standups
Thursday
Wednesday
Tuesday
Monday
Key |  |  |  | 
Daily | Weekly | Fortnightly | Monthly | Quarterly
Scrum of Scrums
Technical Design Authority
Change Board
Steering Committee1
Daily meetings are reduced timeslots
Steering Committee1 – Usually the last 2 weeks of the month, day and timings can vary
Sponsor Review1 – Occurs every month excluding Steering Committee months
Scrum of Scrums, Dependency Forum and Change Board to start in Inception
Sponsor Review2
Business Design Authority
Daily Standups
Scrum of Scrums
Daily Standups
Scrum of Scrums
Daily Standups
Scrum of Scrums
Daily Standups
Scrum of Scrums
Programme Management Update
Procurement Update
PMO RAID review
Dependency Forum
Leadership Stand-Up
Business Update
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 24: Escalation process
Executive Level:
Other key stakeholders:
Finance modernisation
Underwriting & Servicing
Data Migration
Operations
Business Sponsor
Business SMEs, Business Analysts, Architects, Engineers, UAT team etc.
Project Team:
Business Analysts, Architects, Designers, Engineers, QA / Testers, DevOps, Scrum Masters, Data Scientists
Delivery Executive
Account Executive
Escalations
Decisions / Actions
Escalations are done jointly from Capgemini and Beazley representatives from one level to Capgemini & Beazley representatives at the next level up.
Prior to escalation, representatives will work together to:
Agree what they agree on
Agree what they disagree on
Prepare for the escalation, making clear:
  The problem statement
  The options for resolution and their pros and cons
  The decision(s) and / or action(s) required
  The date required by
  The impact of doing nothing / missing the date
Escalation Etiquette:
Product Owner
Functional Lead
Delivery Lead
Delivery Lead
Programme Director
Programme Director
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 25: Change control
Change Implementers
Change Recorder / PMO
Change Reviewer(s) & Sponsor(s)
Change Board
Present for Approval to IA
Deploy
End
Develop
& Test
Yes
Change Requestor
Start
Secure Sponsor & Submit CR
Create Change Request
Produce the IA
(delivery IA & Business Impact of not proceeding)
No
Review the IA
Present for Approval to Deliver
Accept?
Proceed?
Create / Update User Story
Consider for Backlog
Review the CR
Yes
No
Align on the Gap / Defect / Additional Requirement being a change
Assign CR Ref, Update Change Log, Update CR (with IA) & Drive the Change Control Process
Update Scope / Plan / Budget
Controlling change via an agreed process that acknowledges it is needed but manages its impact for the good of delivery is key to the success of this largescale programme delivery.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 26
Tools to be provided by Beazley for delivery
Project Tools
VDI provisioning
Outlook, MS Teams
Project planner
Microsoft Office tools- word, excel, ppt
Guidewire sandbox access
Process and support to raise additional software requests
Discovery Tools listed below is not an exhaustive list and will be further built out ….
Lewis Claxton (Beazley PMO)
Dev & Test Team Tools
JIRA
Confluence
Guidewire Platforms
Microsoft Visio
Beazley
Inception
Managed by
Managed by
TOOLS FOR INCEPTION
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 27
Process to setup projects in Jira with one scheme configuration and upload prioritized backlog during inception phase
Jira Setup
GPAS &Billing Projects
Screen Scheme
Workflow Scheme
Issue type Scheme
Permission Scheme
Step1 – Create one Schema Configuration for all GPAS projects
Step2 – Create Projects and set one scheme configuration
Step3 – Upload the prioritized backlog to GPAS projects
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model