## Slide 1: Beazley gpas OPERATING MODEL
Drafted: Mar-2024
Ways of Working for GPAS Programme Delivery

## Slide 2
S.No | Version | Month/Date | Changes made
1. | 0.1 | March-2024 | First version of Ways of working, focused more at Inception phase method & processes
  Document change history

## Slide 3: CONTEXT
Ways of working is a Capgemini recommended way of Program execution allowing all relevant parties and stakeholders to operate and collaborate towards achieving the common program goals. This document intends to target both processes and behaviours that form the building blocks of successful completion of GPAS
This Ways of working is specifically designed for GPAS only and for the scope of work owned by Capgemini. The processes, behaviours and recommendations outlined here may not be applicable outside GPAS to the wider Modernization program
The Ways of working document is expected to evolve iteratively, through Inception phase before it can be made final. However, throughout the GPAS program execution, the delivery method or process may undergo change in certain sections if all the influenced parties agree there is a need for improvement

## Slide 4: Ways of working
Scope of Inception phase
Key Success factors
Inception activities – week wise split
Workshops – rules of engagement
Key roles – Beazley and Capgemini
Team Structure for Inception
Design Principles
Inception phase deliverables
RACI
Governance – Key roles, Cadence, Escalation, Change Control
Tools for Inception
JIRA set-up and governance
To be built & agreed in parallel to Inception for start of build
  Foundation & Waves Construct
  Backlog management process
  Sprint construct
  Cadence and ceremonies
  User story management
  Activities list
  DoD and DoR - Definition of Done and Definition of Ready
  Third party alignments and SLA
  Metrics & Reporting
  Collaboration and Tool sets
INCEPTION PHASE
BUILD PHASE
The immediate focus is to draft and agree on a Ways of working applicable for the start of Inception phase. As a next step, Ways of working will be extended to document methods and processes applicable to the Build phase.
To be built & agreed for start of Inception

## Slide 5: Programme Inception phase helps create the foundation & vision of the Transformation
Foundation Release Mobilization is focused on enabling MVP Design and Build to start
Build the foundation with core principles intact. – data/ automation / experience
Collaborative pre-work on entry criteria to ensure rapid start and timely completion
Transform the plan from the Inception to reality, transforming the business requirements to functional systems
Plan for future Releases and LOB
Confirm Roll-out Approach
Programme Inception
Design and Build
Programme Inception is focused on “Designing the next winning proposition”
A common 12-weeks Programme Inception phase to clarify and align the scope in all Products for a Foundation, followed by the implementation of the planned Releases.
What you’ll get:
Prioritized backlog
High Level Design
Foundation release plan
Key risks & assumptions
Dependencies detailed

## Slide 6: KEY SUCCESS FACTORS
Right Time
  Multi-day sessions
  Aligned workshops
  Covering India, UK and US time zone
Right Inputs
  Product / Process Design
  OOTB Guidewire Process Flows
  Interfaces
Right Enablers
  Guidewire Instance
  Collab Tools
  Reliable access to VDIs
Inception Phase Principles
OOTB Conformance
Business Priority / Rationale
Design for Future
Outputs more focused at Foundation release
GPAS Ways of working
Prioritized Backlog
Effort & Resourcing
GPAS HLD and Delivery Plan
Migration Strategy
Integration Inventory
Dependency tracker
Test Strategy
Rationalized Product set for
Pebbles / Rocks / Boulders
Categorizing elements of solution for appropriate escalation to finalise scope
Right Team
  Product Owners, Business SME
  Right Capgemini team
  Collaboration is key
Right Decisions
  Timely & accurate decisions
  On time escalations for help
  Lean thinking
AGILE
MATURITY
COLLABORATION
DEPENDENCIES MANAGEMENT

## Slide 7: INCEPTION PLAN – By WEEK BREAKDOWN
Workshops - Tuesday, Wednesday, Thursday
(AM: 10-12:30
PM-13:30-17:00)
The Inception plan will be shared separately for Beazley’s review and preparation for start

## Slide 8
Rules of Engagement
  All meeting and workshop invites to include:
    Purpose of the meeting / Agenda
    Input to the meeting
    Expected output from the meeting
    Deliverable(s) output (as required)
  Be straight and transparent
  Business attendees and availability to be confirmed by Beazley (Senior Product Owner/relevant Product Owner) before invitation is sent
  Parking lots/Decision logs to be captured and logged in the required trackers
  Critical decisions to go through appropriate Programme Governance forums and documentation
  On site and remote attendance options to be available
  Recording of sessions to be used where appropriate
  All sessions to be aligned to overall programme strategy
  All material to be utilised for Beazley programme purposes only
Guidelines for meetings and workshops
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 9: Inception programme deliverable outputs
Functional Activities
Obtain an understanding of in scope functional areas
Obtain and understanding of as is current processes
Receive demos of current systems
Review the existing capability map and identify any gaps
Deliverables at programme level & expected signatories
Deliverable Names | High level Description and Expectation | Sign Off
PD1: GPAS Ways of Working | Detailed methodology, Governance model, Change control model, communication management, Reporting & meeting cadence, Initial team structure, RACI, Escalation approach, Tools for build & usage boundaries | Warren Pilkington Stephen Payne Troy Baillargon
PD2: Prioritized Backlog (Foundation) | Documentation of Foundation Release Functional requirements, in scope Epics/Features. User Stories scope statement defined in excel format for uploading into JIRA | Jeff Colandrea Matt Reynolds
PD3: Resourcing & Efforts (Foundation) | Breakdown of resourcing needs (by quarter) aligned to effort and bottom-up estimation of Epics and Features against the delivery plan. High level scope, budget, and resourcing/effort should reconcile. | Programme Leadership team
PD4: Delivery Structure & Plan (Foundation) | Phase & Workstream definitions, objectives and milestones. Verification and Acceptance. Plan detailing the Guidewire sprint plan, number of sprints, dates, and high-level proposed scope breakdown. | Warren Pilkington Athik Miah
PD5: GPAS High Level Design | Aligned to agreed architecture decisions and principles Detail how Policy and Billing Center will fit into Beazley ecosystem. Detail the key Integrations for the Foundation release | Dean Johnston Matt Reynolds
PD6: Migration Strategy | Approach to migration in terms of execution and timing. High-level data requirements at an entity level, from relevant business areas. | TBD
PD7: Integration Manifest | Inventory of integrations defining cardinality, service contract ownership, integration pattern or method, initial view on complexity. Definition of any intermediated services or gateways to influence design. | TBD
Deliverables to be produced during Inception, ready for review and response feedback loop. All deliverables to have a wider review distribution which will be confirmed on the deliverable itself.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 10: Inception programme deliverable outputs
Functional Activities
Obtain an understanding of in scope functional areas
Obtain and understanding of as is current processes
Receive demos of current systems
Review the existing capability map and identify any gaps
Deliverables at programme level & expected signatories
Deliverables to be produced during Inception, ready for review and response feedback loop. All deliverables to have a wider review distribution which will be confirmed on the deliverable itself
Deliverable Names | High level Description and Expectation | Sign Off
PD8: Detailed Dependency Tracker | Internal and External Dependencies detailed with dates and deliverables agreed with each of the related parties. | Warren Pilkington
PD9: Functional & Technical Principals | Functional and Technical Design principles documented. | Dean Johnston Matt Reynolds
PD10: GPAS Test Strategy | High level scope of key test phases, gates and entry/exit criteria; view of resourcing. Input into Definition of Done (DoD) including acceptance criteria, automation definition. Definition of the GPAS environment requirements and when they will be required by to meet the timelines. | TBD
PD11: Product Set | Rationalised product set for foundation release Identification of any products requiring further analysis and key decision papers where necessary. | Warren Pilkington
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 11: Team Structure for inception
Architects
Technical Leads
Delivery Leads
Product Owner
Test Manager
Subject Matter Experts
Brett Fabian-Smith
Vamshi Chennamadhavuni
(Guidewire)
SivaramaKrishna Narayanan
Athik Miah
(BC)
Jeff Colandrea
(Core)
Patrycja Kuligowska
(BC)
Dean Johnston
TBD
Devin Wells
(CIPS)
Troy Baillargeon
(Change)
Stephen Payne
(GPAS)
Matt Reynolds
Gourab Marik
(INT)
Balaji KV
(BC)
Programme Directors
Max Cartwright
Warren Pilkington
Ananda Arasu Ponnaiah
Natraj Gudla
Product Rationalization
Business Sponsors / Delivery Executives
Vanesssa Ortega
Procurement
Ian Craney
Ben Lowles
Abby Vredenburg
(Op)
Beazley
Capgemini
Barry Houston
Akhlas Hafiz
Jigar Solanki
Functional Leads
Sherezad Contractor
(PC)
Sriram Jagannathan
(BC)
Peter Dixon
Kelly Reisling
Jeff Colandrea
(Core)
Troy Baillargeon
(Change)
Matt Reynolds
Rajesh Bandaru
(PC)

## Slide 12: Design principles
support the agreed Release scope?
ensure the business is not in a worse position from before?
support a move off existing systems
support flexibility and maintainability for future releases?
All key decisions to move through formal programme governance decision bodies
abide by the Beazley architectural principles?
Does the decision:
allow for scalability and is not closed off for future-states
Decision making process:
Workshop/Meeting where key question arises
Identification of key decision needed, decision owner and required inputs to enable decision
Creation of key decision paper and supporting material(s)
Presentation at BDA/TDA or both as required
BDA/TDA decision output documented and stored
Ratification of BDA/TDA decision output at Programme Leadership/Steering if required
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 13: KEY AREAS - raci
A | Accountable | Authority and decision making
R | Responsible | Responsible for actualisation of the task
C | Consulted | Engaged stakeholder, consulted in decisions, delivery and approach to enable their input
I | Informed | Informed stakeholder receiving updates and outputs only
Key
RACI will also be broken down further into detailed responsibility lines.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 14: KEY ROLES – Beazley
Role | Named Resource | Responsibilities
Business Owner/ Sponsor | Vanessa Ortega | Approve scope, target design and execution plans for the PAS iniaitive. Accountable for delivery against OKRs, business outcomes and benefit realisation. Commits or helps facilitate appropriate resources (e.g. SMEs) and support issue resolution for the PAS initiative. Approve and oversee key initiative decisions as adviser Steer solution design and build based on business needs
PAS Delivery Lead | Warren Pilkington Athik Miah | Develop the initiative objectives, scope, highlevel implementation roadmap, resource requirements and investment estimates. Working with the delivery partners, create and manage the PAS delivery plans. Manage the delivery teams inc. resource management, supply & demand, technical capability and skills Manage inbound and outbound dependencies needed for the delivery of the component Management of risks and issues impacting progress Responsible for status reporting of the project
Global PAS Product / Platform Lead | Stephen Payne | Helps define the PAS Product Strategy, Vision and Roadmaps alongside the Product Owners in the PAS initiative. Managing and prioritising the PAS Portfolio Backlog taking care to ensure alignment with business architecture, data teams and existing BAU environments. Delivering Value by ensuring the PAS solutions are complete from the user perspective (including operations, change etc) and deliver meaningful business value. Point of escalation and coaching for squad-level Product Owners.
Solution Architect Lead | Dean Johnston Matt Reynolds Steve Enness | Work with squads to define target technical solutions. Gain approval through Design Authority for technical solutions. Monitor technical risk and mitigation control. Define technical guardrails for delivery squads. Embed technical work into backlogs of delivery squads.
Product Owner | Jeff Colandrea Devin Wells | There will be different Product Leads depending on the release/wave of PAS implementation. For example, Cyber and D&O in Foundation release. Understand and be able to describe the end-to-end solution in a high level, the use cases and related business drivers. Attend decision making sessions, feeding input regarding the product and its interaction with other components, acting as a point of reference for the product required features and behaviour. Understand business demands and requirements and translate these into solutions that are refined iteratively and present them to the team. Prioritise requirements of the product and make adjustments as needed after each release. Define the future goal of the product (the ‘product vision’) Maintain and own the product backlog. Accepting or rejecting suggested improvements. Report progress, involvement in governance arrangements.
Scrum Master | TBD | Responsible for the effective and consistent operational performance for the scrum process. Responsible for both timely and effective tracking and reporting on team progress against goals. Responsible for managing team capacity, utilisation and velocity. Responsible for providing Delivery Lead and Product Owners with relevant input for each team member to support each team member’s development and performance needs.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 15: KEY ROLES – Beazley
Role | Named Resource | Responsibilities
Quality Assurance Testing Lead | TBD | Ultimately accountable for the quality of the overall end to end solution Provides overall QA oversight for test design and execution, striving for commonality where appropriate Accountable for defining Program level test strategies and approaches for all test phases Accountable for planning and oversight of all test phases, including UAT Provides testing oversight and direction, drives execution of testing strategies and manages testing related objectives and issues across the Program
Release Train Engineer/ Manager | Stephen Payne Marta Latuszek | Partnering with Product Manager Assisting in management of risks, issues and any potential roadblocks Responsible for resolving contingencies and complicated issues, provide leadership to project teams, and act as a consultant/coach to management Responsible for DevOps and improvement of workflow
Business Architecture Lead | Dean Johnston | Accountable for developing the business architecture strategy Applying structured business architecture approach and methodology Drives and facilitates the right discussions with business leaders to identify business capabilities in relation to current and future business objectives Responsible for presenting recommendations and solutions clearly and concisely Accountable for a specific LOB, business pillar or multiple segments, and high level of complexity and attributes
Change Management Lead | Troy Baillargeon | Responsible for managing all types of change Evaluates the impact of change Supports development of communications relevant to change initiatives Accountable for defining success metrics and measuring performance against these
Training / Communication | Lewis Claxton | Coordinating the development, execution, refinement, and measuring the impact of programme outreach, communications, and knowledge management strategies Responsible for coordinating development of training / learning materials Accountable for the organisation, coordination of workshops and events Responsible for supporting communications, knowledge management, and training activities
Delivery Partners (Third party suppliers to Beazley) | TBD | Partner with the Senior Delivery Lead Manage the scope of services in support of delivering the PAS initiative Manage the deliverables to be produced in support of delivering the PAS initiative Manage any CRs related to the component and services being provided in support of delivering the PAS initiative Create and manage the plans for the delivery of the services in support of the PAS initiative Manage the delivery squads inc. resource management, supply & demand, technical capability and skills Jointly manage sprint planning, retrospectives and reporting relating to services being provided in support of delivering the PAS initiative Manage inbound and outbound dependencies needed for the delivery of the component Coordinate activities and schedule across the PAS initiative Management of risks and issues impacting progress
Delivery Squads (Beazley SME and/or Third party suppliers to Beazley) | TBD | End-to-end delivery of each product Provide requested SME input into tasks, activities, decisions Flag risks and issues to the Senior Delivery Lead and/or Delivery Partner Proactive updating of Jira, the backlog and the sprint boards in conjunction with the scrum master
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 16: KEY ROLES - capgemini
Role | Named resource | Description | 
Delivery Executive | Barry Houston | Responsible for overall Services quality and delivery Assist in the resolution of issues and change controls | Prepare for and support Steering/Policy Executive Advisory Group Meetings Monitor program progress
Program Director | Max Catwright | Responsible for in-scope Program activities Provide Program status reporting on a regular basis to Beazley Program and Executive Leadership | Responsible for overall Services quality and delivery of the Program Responsible for day-to-day management and tracking of the in-scope Program activities
Engagement Manager | Ananda Arasu Pommaiah | Manage the detailed Program plan in collaboration with Beazley Leadership Team Provide Program Status reporting on a regular basis to Beazley Program Leadership | Facilitate Decisions, Issues and Risk management across the core program and escalate to Beazley in advance of the materialization of potential risks and issues that may delay the program. Assist the resolution of issues and change controls
India Delivery Executive | Natraj Gudla | Manage the detailed Program plan in collaboration with Beazley Leadership Team Provide Program Status reporting on a regular basis to Beazley Program Leadership | Facilitate Decisions, Issues and Risk management across the core program and escalate to Beazley in advance of the materialization of potential risks and issues that may delay the program. Assist the resolution of issues and change controls
Product Rationalisation | Peter Dixon Kelly Riesling | Provide subject matter specialist advice with regard to overall business requirements and product backlog Provide input on solving business problems within the defined application landscape by working with the business and Technical resources. | Coordinate with Functional Lead and Technical architect to help define implementation scope of work.
Enterprise Architect | Brett Fabian-Smith | Provide leadership and architectural expertise across a broad set of technologies, including integration & middleware technologies Consult with and advise the Program team on technology and strategic decisions | Identify architectural constraints for the architectural level (project, domain, application) based on technical and organizational requirements Provide subject matter specialist advice with regard to overall solution architecture and technology
PolicyCenter Functional Lead | Sherezad Contractor | Provide Policy subject matter experience Work with Beazley business leadership to drive overall business requirements | Provide leadership and direction for elaboration and RSWs Provide joint review and approval of deliverables
BillingCenter Functional Lead | Sriram Jagannathan | Provide Billing subject matter experience Work with Beazley business leadership to drive overall business requirements Provide leadership and direction for elaboration and RSWs | Provide joint review and approval of deliverables Lead with the high-level implementation approach for complex functional requirements
PolicyCenter Technical Lead | Vamshi Chennamadhuveni | Provide subject matter specialist advice with regard to GW PC Conduct configuration option analysis to support business requirements Provide input on GW PC best practices, constraints, and effort during workshops, including pre-work | Provide input on effort and impact associated with potential configurations/customizations Support the Policy Functional Lead with the high-level implementation approach for complex functional requirements
BillingCenter Technical Lead | Sriram Jagannathan | Provide subject matter specialist advice with regard to GW BC Conduct configuration option analysis to support business requirements Provide input on GW PC best practices, constraints, and effort during workshops, including pre-work | Provide input on effort and impact associated with potential configurations/customizations Support the Policy
Integration Lead | Saharsh Gupta Gourab Marik | Provide integration and technical architecture guidance for GW Lead analysis effort of interface specification documents | Lead the integration design effort for specified integration points Provide direction and technical guidance
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 17: KEY ROLES - guidewire
Role | Named resource | Description
PolicyCenter Principal Architect | TBD | PolicyCenter technical architect
PolicyCenter Principal Business Analyst | TBD | PolicyCenter functional and product expert
BillingCenter Principal Architect | TBD | BillingCenter architect
Integration Principal Architect | TBD | Guidewire Integration architect
London Market Specialist | TBD | Guidewire London Market and product architect
Guidewire Delivery Management (non-billable part time role) | TBD | Guidewire point of contact for the implementation and Guidewire assigned resourcing.
Guidewire Product (non-billable part time role) | TBD | Guidewire London Market expert and point of liaison with Guidewire product team. Needs to understand the business needs so that any future Guidewire product related enhancements can be planned.
Guidewire Product (non-billable part time role) | TBD | Guidewire London Market expert and point of liaison with Guidewire product team. Needs to understand the business needs so that any future Guidewire product related enhancements can be planned.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 18: governance
The overall success of this engagement will be based on close collaboration between all parties, transparency and fact-based decision making. We will also use this Governance process to keep us all collectively honest and true to the Programme objectives.
Daily
Weekly
Monthly/Quarterly
Weekly
Sponsor Review
Change Control Board
Dependency Review Forum
Technical Design Authority
Business Design Authority
RAID Review
Agile – Daily Stand-up / Scrum of Scrums
GPAS Programme Management Update
Decisions
Decisions
Reporting
Reporting
Procurement Update
SteerCo
Leadership Update
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 19
Proposed Programme CADENCE
Friday
9.00 – 9.30 |  |  |  |  | 
10.00 – 10.45 |  |  |  |  | 
11.00 – 12.00 |  |  |  |  | 
12.00 – 13.00 |  |  |  |  | 
13.00 – 14.00 |  |  |  |  | 
14.00 – 15.00 |  |  |  |  | 
15.00 – 16.00 |  |  |  |  | 
16.00 – 17.00 |  |  |  |  | 
Daily Standups
Thursday
Wednesday
Tuesday
Monday
Key |  |  |  | 
Daily | Weekly | Fortnightly | Monthly | Quarterly
Scrum of Scrums
Technical Design Authority
Change Board
Steering Committee1
Daily meetings are reduced timeslots
Steering Committee1 – Usually the last 2 weeks of the month, day and timings can vary
Sponsor Review1 – Occurs every month excluding Steering Committee months
Scrum of Scrums, Dependency Forum and Change Board to start in Inception
Sponsor Review2
Business Design Authority
Daily Standups
Scrum of Scrums
Daily Standups
Scrum of Scrums
Daily Standups
Scrum of Scrums
Daily Standups
Scrum of Scrums
Programme Management Update
Procurement Update
PMO RAID review
Dependency Forum
Leadership Stand-Up
Business Update
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 20: Escalation process
Executive Level:
Other key stakeholders:
Finance modernisation
Underwriting & Servicing
Data Migration
Operations
Business Sponsor
Business SMEs, Business Analysts, Architects, Engineers, UAT team etc.
Project Team:
Business Analysts, Architects, Designers, Engineers, QA / Testers, DevOps, Scrum Masters, Data Scientists
Delivery Executive
Account Executive
Escalations
Decisions / Actions
Escalations are done jointly from Capgemini and Beazley representatives from one level to Capgemini & Beazley representatives at the next level up.
Prior to escalation, representatives will work together to:
Agree what they agree on
Agree what they disagree on
Prepare for the escalation, making clear:
  The problem statement
  The options for resolution and their pros and cons
  The decision(s) and / or action(s) required
  The date required by
  The impact of doing nothing / missing the date
Escalation Etiquette:
Product Owner
Functional Lead
Delivery Lead
Delivery Lead
Programme Director
Programme Director
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 21: Change control
Change Implementers
Change Recorder / PMO
Change Reviewer(s) & Sponsor(s)
Change Board
Present for Approval to IA
Deploy
End
Develop
& Test
Yes
Change Requestor
Start
Secure Sponsor & Submit CR
Create Change Request
Produce the IA
(delivery IA & Business Impact of not proceeding)
No
Review the IA
Present for Approval to Deliver
Accept?
Proceed?
Create / Update User Story
Consider for Backlog
Review the CR
Yes
No
Align on the Gap / Defect / Additional Requirement being a change
Assign CR Ref, Update Change Log, Update CR (with IA) & Drive the Change Control Process
Update Scope / Plan / Budget
Controlling change via an agreed process that acknowledges it is needed but manages its impact for the good of delivery is key to the success of this largescale programme delivery.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 22
Tools to be provided by Beazley for delivery
Project Tools
VDI provisioning
Outlook, MS Teams
Project planner
Microsoft Office tools- word, excel, ppt
Guidewire sandbox access
Process and support to raise additional software requests
Discovery Tools listed below is not an exhaustive list and will be further built out ….
Lewis Claxton (Beazley PMO)
Dev & Test Team Tools
JIRA
Confluence
Guidewire Platforms
Microsoft Visio
Beazley
Inception
Managed by
Managed by
TOOLS FOR INCEPTION
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 23
Process to setup projects in Jira with one scheme configuration and upload prioritized backlog during inception phase
Jira Setup
GPAS Projects
Screen Scheme
Workflow Scheme
Issue type Scheme
Permission Scheme
Step1 – Create one Schema Configuration for all GPAS projects
Step2 – Create Projects and set one scheme configuration
Step3 – Upload the prioritized backlog to GPAS projects
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 25: Ways of working
INCEPTION PHASE FOCUSED – for start of Inception
Overall view of the Delivery phases
Scope of Inception phase
Inception phase construct – week wise split of activities & deliverables
Entry and Exit criteria
Governance – Capgemini & Beazley (key roles from Business, Capgemini, Architecture etc)
Cadence (covering US and UK time zones)
Pre-requisites & RACI
Tools for Inception
JIRA set-up and governance
BUILD PHASE FOCUSED – to be built during Inception phase
  Foundation & Waves Construct
  Backlog management process
  Sprint construct
    User story construct
    Elaboration and design phase break-up
    User story cycle
    Sprint events and RACI
    Sprint on a timeline
  Cadence and ceremonies
    Roles and ceremonies matrix
  User story management
    Scenario's illustration
  Activities list
  Definition of done and definition of ready
  Third party alignments and SLA
  Metrics
  Collaboration and Tool sets

## Slide 26
Needs to be updated for beazley
Communications planning and execution is a tool to clarify goals and objectives
Engage
Project Initiation communications to engage the business
Check Ins
Monitor Progress with business
Weekly
Updates
Regular comms out to business areas (e.g. All Hands calls)
Ongoing
Podcasts
Senior updates
Ongoing
ASE
Kick off and Alignment
Communications will clarify our objectives and goals for all key stakeholders
Communications will be driven by Beazley to ensure regular alignment and insight
The end-to-end communications plan will be written as input to readiness for the Discovery phase
A proposed structure/flow is shown below
NOTE: Beazley are developing a set of templates to be used for programme communications
Programme Communication
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 27: Inception & Foundation Release
Roles & Scrum team view
Inception
Product Owners (Policy, Billing, Integrations)
Business SMEs
E2E Programme Lead
E2E Programme Test Lead
Architects
Foundation Release
Programme Lead
Delivery Lead
Architect
Functional Lead
Business Analysts
Workstream Lead
Programme Test Lead
Lead Dev Engineer
Beazley
Capgemini
Guidewire
Engagement Lead
Assurance Lead
Assurance Architect
Product Owners (Policy, Billing, Integrations)
Business SMEs
E2E Programme Lead
E2E Programme Test Lead
Architects
Programme Lead
Delivery Lead
Architect
Functional Lead
Business Analysts
Workstream Lead
Programme Test Lead
Scrum Master
Lead Dev Engineer
Dev Engineer
Test Engineer
DevOps
Engagement Lead
Assurance Lead
Assurance Architect
Scrum Teams
PolicyCenter
BillingCenter
GPAS & Billing INT for UWWB
Rest of Integrations
Migration
Product
Notes: 5 to 8 mins
Talk about, we understand the need for interim & target state, possi

## Slide 28: Inception programme deliverable outputs
Needs to be updated for beazley
Functional Activities
Obtain an understanding of in scope functional areas
Obtain and understanding of as is current processes
Receive demos of current systems
Review the existing capability map and identify any gaps
Deliverables at programme level & expected signatories
Deliverable Names | High level Description and Expectation | Responsible | Sign Off
PD1: High Level Foundation release scope definition | Release Roadmap and confirmed Release 1 scope | CG, SFPS, TRV | Christian Kitchen Bill Devine Michael Lawton
PD2: Ways of working for Discovery | Defined and agreed governance, roles/responsibilities, structure and comms for Discovery phase | CG, SFPS, TRV | Programme Leadership Team
PD3: Rationalised product set for foundation release | Identification of outlier products or gaps in product sets requiring more analysis, driving key decision papers where required | Lead Business Architect, Senior Product Owner | Kieran O’Grady
PD4: Architecture Decision & Principles (Draft) | Draft approach to solution design, agreed principles and design patterns. | CG, SFPS TRV | Sam Kesseli
PD5: Application Architecture Blueprint (Draft) | Draft set of in-scope applications and components | CG, SFPS TRV | Sam Kesseli
PD6: High Level Product backlog | High level Epic/Feature list confirmed for Release 1 scope | Lead Business Architect, Senior Product Owner | Kieran O’Grady
PD7: e2e project plan | Pre-Inception and Discovery plan; and high level draft end to end plan | CG, SFPS TRV | DeAnna Dobosz Barry Houston
PD8: Capability map approved | Confirmed capability map aligned to Release 1 scope – This includes the visual capability map on a page and the supporting excel workbook | TRV | Kieran O’Grady Rob Harwood
Deliverables to be produced during Pre-Inception, ready for review and response feedback loop from Week 7 into Week 8 (end of Pre-Inception). All deliverables to have a wider review distribution which will be confirmed on the deliverable itself.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 29: Inception programme deliverable outputs
Needs to be updated for beazley
Functional Activities
Obtain an understanding of in scope functional areas
Obtain and understanding of as is current processes
Receive demos of current systems
Review the existing capability map and identify any gaps
Deliverables at programme level & expected signatories
Deliverable Names | High level Description and Expectation | Responsible | Sign Off
PD9: Communications plan | Reporting, frequency, expected audience and business comms required for FOS programme | CG, SFPS, TRV | DeAnna Dobosz
PD10: Functional workshop plan for Discovery | Functional workshop plan for high level requirement gathering | CG, SFPS, TRV | Kieran O’Grady
PD11: Initial version of Integration Manifest | Inventory of any integrations and intermediary services including definitions, ownership, high level design etc | CG, SFPS, TRV | Sam Kesseli
PD12: Technical Workshop plan | Technical workshop plan to gather and define integration requirements | CG, SFPS, TRV | DeAnna Debosz Barry Houston Rob Harwood
PD13: High-level end to end customer journey map | The high-level future state processes and end-to-end journey for the identified personas. The journey map will highlight the key touchpoints for the identified personas across the customer lifecycle and will be an input to the Capability Map and product backlog. Refinement of the future state Blueprint and Wireframes to be conducted during Discovery. Document describing how the capabilities from the e2e customer journey map will be delivered through the Application | SFPS, TRV | Mark Wright Kieran O'Grady
Deliverables to be produced during Pre-Inception, ready for review and response feedback loop from Week 7 into Week 8 (end of Pre-Inception). All deliverables to have a wider review distribution which will be confirmed on the deliverable itself.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 30: TEAM STRUCTURE
Scrum Master
Business Analysts
Product Owner
Business SMEs
Developers
GW Consultants
Tech Lead
Developers
Testers
Test Lead
Consultants
Test Lead
Executive Leadership
Program Leadership
Delivery Teams
Test Manager
Functional Lead
PMO
PMO
Programm
Programme / Delivery
Management
Capgemini Exec Sponsor
Steering Committee
Executive Sponsors
Infrastructure Lead
UAT
Product Owner(s)
Capgemini
Beazley
LEGEND
Sapiens
Scrum Master
Business Analysts
Dev Lead
Product Owner
Business SMEs
Developers
GW Consultants
Business Analyst
Tech Lead
Developers
Testers
PC Conv Dev
Policy
Onshore
Offshore
Scrum Team
Offshore Delivery Lead
Configuration Lead
Integration Lead
Release Manager
Leaders ensure alignment between Scrum teams
Data Lead
Integration
Scrum Master
Integration Dev
Integration Dev
Technical SMEs
Developers
GW Consultants
Mapping Analyst
Tech Lead
Developers
Testers
Architects
Billing
Test Lead
Automation Testers / Performance Testers
Test Leads
OCM Lead
ALTERNATIVE TO SLIDE 7 - Needs to be updated for beazley
Functional
Leads
Technical
Leads
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 31: Team for inception
Needs to be updated for beazley
Rob Harwood
Technical Design Authority Lead
Programme Leadership
Technology
Business
Sponsor(s)
Greg Toczydlowski
Steering Committee
Maryellen Szwez
Int’l Programme Lead
Andrzej Kobus
Ent Archt & Emerging Tech
Bill Devine
Business Capabilities, BI
Kevin De Sa
Digital Enablement
Christian Kitchen
FOS EUR Programme Lead
Jane Marrison
Information Management
Maria Olivo
Mojgan Lefebvre
Matthew Wilson
FOS Programme Sponsor
TBD
Data Tech Lead
Sam Kesseli
Lead Architect
Andy Wilkins
Software Engineering EUR
Dean Martin​
Lead Architect EUR
Kieran O’Grady
Business Design Authority Lead
Pete McConnell
Finance Europe
Chris Allison
BI Specialty
Mike Lawton
FOS Business Owner
Jon Davies
Bond & SI International
Mike Byam
B&SI Project Manager
Jeff Klenk
Rob Harwood
Programme Technical Lead
Kieran O’Grady
Programme Business Lead
DeAnna Dobosz
Programme Director
Bryan Bonadies
Intl CIO
Key Stakeholders
Specialty
Bill Devine
Execution Leadership Support
Underwriting & Portfolio Mngmnt
Operations
Finance & Reinsurance
B&SI
Actuarial & CAT
Claim
Regulatory & Compliance
Emma Scopino
SP&E and CX BI
James Dale
Capgemini Programme Manager
Mary Engdahl
Salesforce Engagement Lead
Barry Houston
Capgemini Programme Director
Brett Fabian-Smith
Lead Enterprise Architect
Peter Dixon
Business Architect
Prasanna Kumar
Data Architect
Vamshi C
Guidewire Architect
Aurobinda Mahapatra
Integration Architect
Segun Odubiyi
PC Functional Lead
Sriram Jagannathan
BC Functional Lead
Mark Conlan
SF User Experience
High Level View – detailed project team chart to be found on next slide
Tim Warburton
Salesforce Programme Architect
Salman Sheikh
Salesforce Solution Architect
Brett Fabian-Smith
Lead Enterprise Architect
Jamie Jones
iHUB Fos Circle Lead
Harsha Chinnam
iHUB FoS Tech Lead
Bradley Todd
Int’l Info Architect
Heather Batchelor
CUO, BI
Greg Toczydlowski
President, BI
Design Authorities
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 32
Integration Design / BA
Aurobinda Mahapatra (S) – Integration Lead
Delivery Management
Programme Sponsorship
Business Architecture, Functional Design and User experience
Capability Guilds
Technology and Data
Business Subject Matter Experts
Underwriting, RI and Portfolio Mgmt
Pricing
Operations
Finance
Claims
Distribution / Customer
Peter Dixon (C) – Lead Business Architect
James Simpson - Senior Business Architect
Colin Small – Business Architect
Mark Wright – UX Lead
Rob Harwood Programme Technology Lead
- Sam Kesseli
Intl Lead Architect
- Stephen Campling (C) Programme Solution Architect
- TBC (C) Programme Data Architect
People, Change & Culture
Steve Chatwin - Training Lead
Steve McKenna – Distribution Lead
Graham Taylor – CRM (BI Retail) Lead
Shanda Davis– BSI UW Lead
Vanessa Hill – BI UW Lead
Callum Rainy-Brown - RI
Elio Buffa -Portfolio Mgmt
Owain Lloyd – Catastrophe Management
Paul Colin – Billing and Settlement Product Owner
Judy O’Neill – Claims Product Owner
Nelly Grelet – Operation - Post Bind / PAS / Servicing Product Owner
Tom Goddard – Product Owner
Transformation Delivery Office
- Richard Kelley - Business Benefits
- Denise Cunningham - Comms Lead
- Pete McConnell – Finance - Ben Cagne – Procurement - Julie Foster - Human Resources
- Imran Shah - Risk & Compliance
Steering Committee
Matthew Wilson – FOS Programme Sponsor
Bill Devine - Executive Leadership Support
Michael Lawton - FOS Business Owner
Christian Kitchen - EUR Programme Lead
Sales and Distribution
Pre-Bind Underwriting
Post Bind/PAS/Servicing
Billing and Settlement
Claims
Accounting Rules / Sub L.
Rating and Pricing
Outwards RI
Data Migration
Delivery Leadership
DeAnna Dobosz - Programme Director
Kieran O’Grady
Programme Business Lead
Alida Liebenberg
Senior Product Manager
Barry Houston( C)
Programme Director
Surya Malladi (C)
Senior Product Manager
Vendor Representation
Vishala Ravipati – Capgemini
Simon Woolrych – Salesforce
Jamie McDonnell – Guidewire
Testing
Discovery onwards - TBC
Beazley Tech Design & Delivery (+downstream)
Data, MI and analytics
Andy Wilkins – Engineering Lead
Vijay Srinivasan – Platform Architect (incl. SF)
TBC - Infrastructure Architect
Salesforce inc SF Design / BA
Angie Rios – SF Product Owner +
Sudheer Sura – Salesforce Platform (Tech) Lead
Mary Engdahl (S) – Engagement Lead
Benjamin Fairclough (S) – Senior Project Manager
Tim Warburton (S) – Salesforce Programme Architect
Ad-hoc Support
Covered by wider team in Pre-Inception
Guidewire inc GW Design / BA
Lorraine Shakesheff (C) – Guidewire Delivery Lead
Denise Wood – Guidewire Platform Owner
Vamshi Chennamadhavuni (C) – Guidewire Enterprise Architect
Covered by wider team in Pre-Inception
Jamie Jones - Data, MI and Analytics Lead
Harsha Vardhan Chinnam – Data Technology Lead
Venkata Konda - Data Governance Lead
Pee T. Lim – Data Architetct INTERIM
Tom Goddard
Product Owner
Nelly Grelet
Product Owner
Paul Colin
Product Owner
Judy O’Neill
Product Owner
Vanessa Hill
Product Owner
Stephen McKenna
Product Owner
Paul Colin
Product Owner
Callum Rainy-Brown
Product Owner
TBC (C)
Data Mig. Lead
Rajeev Jindal (C) - Functional Lead – Sales, Distribution, UW and Pricing
Halim Mahah (C)- Business Analyst 1
Sriram Jagannathan
(C) - Business Design Lead – Policy Admin, Servicing, Billing and Claims
TBC (C) - Business Analyst 1
TBC (C) - Business Design Lead – Accounting Rules and Outwards RI
Arun Kumar (C) - Business Analyst 1
Rupesh Gutula (C) – BillingCenter Functional Lead
KV Balaji (C) – BillingCenter Technical Lead
Segun Odubiyi (C) – PolicyCenter Functional Lead
Arun Showry Pudhota (C) – PolicyCenter Technical Lead – Sales & D, Pre-Bind UW
TBC (C) – PolicyCenter Technical Lead – Rating & P, Post Bind/PAS / Servicing
TBC (C) –Data Lead
Tony Lewis – MI & Analytics Lead
Bradley Todd - Information Architect
TBC – Finance Data Lead
Covered by wider team in Pre-Inception
Product Owners report into Senior Product Manager
Team interfaces
James Dale ( C)
Programme Manager
Rob Harwood
Programme Technology and Data Lead
Capgemini resources (C)
Salesforce resources (S)
Covered by wider team in Pre-Inception
Brett Fabian-Smith ( C)
Lead Enterprise Architect
TBC
Programme Management Office
Mary Engdahl (S)
Salesforce Engagement Lead
Start in Discovery Phase
32
Clare Bodrell – Business Analyst Manager
Jamie Hawkins –Senior Business Analyst
Sindhu Talreja (S)
Solution Consultant
Mark Conlan (S)
Senior Experience Architect
Salman Sheikh (S)
Solution Architect
TBC – Change Lead
Needs to be updated for beazley
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 33: TEAM STRUCTURE
Business Analysts
Product Owner
Business SMEs
Developers
GW Consultants
Tech Lead
Developers
Testers
Test Lead
Consultants
Test Lead
Executive Leadership
Program Leadership
Delivery Teams
Test Manager
Functional Lead
PMO
PMO
Programm
Programme / Delivery
Management
Capgemini Exec Sponsor
Steering Committee
Executive Sponsors
Infrastructure Lead
UAT
Product Owner(s)
Capgemini
Beazley
LEGEND
Sapiens
Scrum Master
Business Analysts
Dev Lead
Product Owner
Business SMEs
Developers
GW Consultants
Business Analyst
Tech Lead
Developers
Testers
PC Conv Dev
Claims
Policy
Data
Onshore
Offshore
Scrum Team
Offshore Delivery Lead
Scrum Master
Business Analysts
Dev Lead
Product Owner
Business SMEs
Developers
Business Analyst
Tech Lead
Developers
Testers
Data Architect
Product Owner
Technical SMEs
Data Analyst
ETL Developers
DataHub Developers
Testers
Configuration Lead
Integration Lead
Release Manager
Leaders ensure alignment between Scrum teams
Data Lead
Integration
Integration Dev
Integration Dev
Technical SMEs
Developers
GW Consultants
Mapping Analyst
Tech Lead
Developers
Testers
Architects
Billing
Test Lead
Automation Testers / Performance Testers
Test Leads
Migration
Product Owner
Technical SMEs
Migration Analyst
Migration Developers
Testers
Migration Lead
OCM Lead
ALTERNATIVE TO SLIDE 7 - Needs to be updated for beazley
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 34: How we will deliver together
Our Delivery framework is based on incremental build, early integration, robust end-to-end quality assurance and early business validation
Iterative for each Release
Design and Build (Sprint Agile)
Hyper care
Stabilization
Pre-Inception
Inception
Missions / OKRs
Initial Estimates
Application Architecture
Ways of Working
Product Rationalization
Product Backlog
Integrated Programme plan
User stories
Estimates
Sprint Plan
Sprint Plan
Sprint Retrosp.
Sprint Review
Testing
Elabora- tion
Config. & Devel.
Prep. Release
Training Users
Acceptance
Release in Production
Outcomes / Enables
Our methodology accelerates the start of large implementations through the reuse of templates, assets and accelerators, obtained from experience of core insurance implementations at a global level.
Env. / Test Strategy
User stories for
OOTB Functionalities
The software is developed during each sprint; tested and usable components are delivered
Early E2E & NFR Testing where possible
Early and continuous acceptance of the delivered Software Business (Early Business Validation)
Internal Knowledge Sharing & Retrospection
Integration Inventory
High level Integration Design
Refinement of Estimates
Refinement of Estimates
Performance Testing
End to End Testing
NFR/OAT Testing
Early Business Validation
Trained Users (OCM)
App. Access
Validation
Business
Acceptance
Transition from the Programme team to the Operations / Support team
Hypercare support (incident analysis, correction and testing)
Business Change
Notes: 4 mins
Robust, tried and tested for GW, taken our experience from 100s of implementations & is based on SAFe
Global delivery methodology
Combination of taking what we have learnt in Pre-Inception, leverage existing GW OOTB / Product Backlog & series of accelerators
We have proven Agile methodology , which we’ll adapt our methodology to specific insurer
Ultimately it’s about best practices, concept of ‘Shift left’, robust frameworks & iterative development

## Slide 35: Org STRUCTURE for inception & Foundational Release
ALTERNATIVE TO SLIDE 7 - Needs to be updated for beazley
Data Analyst
Data Migration Lead
Integrations Squad 1
Tech Architect / Lead
Developer
Business Analyst
Quality Assurance
Developer
Quality Assurance
Data Lead/Architect
Scrum Master
Scrum Master
Functional Lead
Business Analysts
Developer
QA Tester
PAS BAU transition team (dependent on Beazley’s ITOM/ BAU service management structure)
Tech Architect / Lead
Developer
Business Analyst
Quality Assurance
Scrum Master
Technical Analyst / Tester
Infrastructure Lead
DevOps Engineer (s)
Infrastructure Architect
Product Owner
Scrum Master
Functional Lead
Business Analysts
Developer
QA Tester
Product Owner
Scrum Master
Functional Lead
Business Analyst
Developer
QA Tester
Product Owner
Global PAS Platform/ Product Lead (Jeff P)
Business Architecture
Lead (Matt PT 50%)
Enterprise Architect Lead (Dean P)
Billing Lead (Athik P)
SI Delivery Lead
Release Train Engineer/ Manager (Stephen C)
Workbench Workflow/ Process SME- 50%
Rating/ Actuarial SME for D&O and T1 - 25%
Customer/Account Data Management SME - 25%
Agency Management SME - 20%
Billing SMEs (Operations, Receivables, Payable, Finance) - 50%
Customer Service (Ops) Process (Appian) SME - 50%
Migration (Legacy PAS SMEs) - 50% (Multiple)
Product SME (e.g. D&O T1) - 50% (Troy B +1)
Integrations Squad 2
Data Squad
Infrastructure Squad
Product Squad 1 - Core Platform
Product Squad 2 - D&O
Product Squad 3 – Tranche 1
Delivery Organisation
Change Management Lead (C)
Training /
Communication (PT 15%)
Vanessa Ortega (Business Owner)
Warren Pilkington (Delivery Lead)
Core Team
SMEs
Solution Architect
PMO Analyst (Lewis P)
Technical Lead
PAS QA / Test Lead
Billing Squad
Scrum Master
Functional Lead
Business Analyst
Developer
QA Tester
Product Owner
35
Shared Services - IT Security, Risk/Audit, Compliance
Claims SME - 20%
Dauda Jammeh (Fiinance Business Owner)
Joe Bate-Williams(Finance Modernisation Lead)
Guidewire Roles (TBA)
Beazley Resource
SI Resource
Capgemini XXXX
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 36: KEY ROLES - capgemini
Needs to be updated for beazley
Role | Named resource | Description | 
Engagement Director | Barry Houston | Responsible for overall Services quality and delivery Assist in the resolution of issues and change controls | Prepare for and support Steering/Policy Executive Advisory Group Meetings Monitor program progress
Programme Manager | James Dale | Responsible for in-scope Program activities Provide Program status reporting on a regular basis to Beazley Program and Executive Leadership | Responsible for overall Services quality and delivery of the Program Responsible for day-to-day management and tracking of the in-scope Program activities
Delivery Lead | Lorraine Shakesheff | Manage the detailed Program plan in collaboration with Beazley Leadership Team Provide Program Status reporting on a regular basis to Beazley Program Leadership | Facilitate Decisions, Issues and Risk management across the core program and escalate to Beazley in advance of the materialization of potential risks and issues that may delay the program. Assist the resolution of issues and change controls
Business Lead | Peter Dixon | Provide subject matter specialist advice with regard to overall business requirements and product backlog Provide input on solving business problems within the defined application landscape by working with the business and Technical resources. | Coordinate with Functional Lead and Technical architect to help define implementation scope of work.
Enterprise Architect | Brett Fabian-Smith | Provide leadership and architectural expertise across a broad set of technologies, including integration & middleware technologies Consult with and advise the Program team on technology and strategic decisions | Identify architectural constraints for the architectural level (project, domain, application) based on technical and organizational requirements Provide subject matter specialist advice with regard to overall solution architecture and technology
PolicyCenter Functional Lead | Segun Odubiyi | Provide Policy subject matter experience Work with Beazley business leadership to drive overall business requirements | Provide leadership and direction for elaboration and RSWs Provide joint review and approval of deliverables
BillingCenter Functional Lead | Sriram Jagannathan | Provide Billing subject matter experience Work with Beazley business leadership to drive overall business requirements Provide leadership and direction for elaboration and RSWs | Provide joint review and approval of deliverables Lead with the high-level implementation approach for complex functional requirements
PolicyCenter Technical Lead | Vamshi Chennamadhuveni | Provide subject matter specialist advice with regard to GW PC Conduct configuration option analysis to support business requirements Provide input on GW PC best practices, constraints, and effort during workshops, including pre-work | Provide input on effort and impact associated with potential configurations/customizations Support the Policy Functional Lead with the high-level implementation approach for complex functional requirements
BillingCenter Technical Lead | Balaji KV | Provide subject matter specialist advice with regard to GW BC Conduct configuration option analysis to support business requirements Provide input on GW PC best practices, constraints, and effort during workshops, including pre-work | Provide input on effort and impact associated with potential configurations/customizations Support the Policy
Integration Lead | Gourab Marik | Provide integration and technical architecture guidance for GW Lead analysis effort of interface specification documents | Lead the integration design effort for specified integration points Provide direction and technical guidance
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 37: KEY ROLES - guidewire
Needs to be updated for beazley
Role | Named resource | Description
PolicyCenter Principal Architect | Bruno Fauchere | PolicyCenter technical architect
PolicyCenter Principal Business Analyst | Ron Wedderburn | PolicyCenter functional and product expert
BillingCenter Principal Architect | Stephen Hathaway | BillingCenter architect
Integration Principal Architect | Ian Baxter | Guidewire Integration architect
London Market Specialist | Paul Abbott | Guidewire London Market and product architect
Guidewire Delivery Management (non-billable part time role) | Tom Mann | Guidewire point of contact for the implementation and Guidewire assigned resourcing.
Guidewire Product (non-billable part time role) | Mark Rouse | Guidewire London Market expert and point of liaison with Guidewire product team. Needs to understand the business needs so that any future Guidewire product related enhancements can be planned.
Guidewire Product (non-billable part time role) | Paul Mallett | Guidewire London Market expert and point of liaison with Guidewire product team. Needs to understand the business needs so that any future Guidewire product related enhancements can be planned.
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 38: KEY ROLES – Beazley
Role | Named resource | Description
Steering Committee | Greg Toczydlowski, Maria Olivo, Mojgan Lefebvre, Jeff Klenk | Future focused governing body that provides strategic direction, participates in development of business vision, makes material budget, scope, and timing decisions and monitors program progress to ensure alignment with overall program objectives.
Sponsors | Bill Devine, Christian Kitchen, Mike Lawton | The sponsor is accountable for ensuring that the work is governed effectively and delivers the objectives that meet identified needs
EUR Programme Lead | Christian Kitchen | Accountable for the success of the project and owner of the Business case. Attends the steering committee and expedites key decision making process.
FOS Business Owner | Michael Lawton | Accountable for the success of the project and owner of the Business case. Attends the steering committee and expedites key decision making process.
Programme Director (Execution) | DeAnna Dobosz | Responsible for end to end programme delivery, prioritisation; alignment to business outcomes, and delivery of business capabilities.
Programme Business Lead | Kieran O’Grady | Accountable for business outcomes, making program business decisions and setting program business priorities.
Senior Product Manager | Alida Liedenberg | Overall Product Manager with oversight across all the various business areas and individual Product Owners. With support from the Product Owners, will give steering recommendations on decisions to the Programme Business Lead.
Product Owners – Various | Various | BAU owner of the product with the overall decision making authority of the product. Provide function and product requirements. Development and prioritization of the User Stories / Backlog with the scrum master.
Programme Technology and Data Lead | Rob Harwood | Accountable for alignment to technical architecture roadmap and overall technical delivery.
Data, MI and Analytics Lead | Jamie Jones | Accountable for alignment to data and MI outcomes, making programme level decisions and setting data and MI priorities at this level.
International Lead Architect | Sam Kesseli | Accountable for Architecture and technology strategy.
Change Lead | TBD – for future phase | Develops Change Plan for stakeholders, communications plan, and oversight of Change Management activities.
Training Lead | Steve Chatwin | Develop Training Plan, Training Materials and oversight of execution of Training delivery
Finance Lead | TBD – for future phase | Accountable for alignment to Finance outcomes, making programme level decisions and setting Finance W/S priorities at this level.
Data Migration Lead | TBD – for future phase | Accountable for alignment to data migration outcomes, making programme level decisions and setting data migration priorities at this level. Works very closely with the Technology and Data leads.
Test Lead | TBD – for future phase | Overall Test Lead, responsible for Test Strategy, Test scope, end to end engagement with business and exit gate criteria and sign offs.
Needs to be updated for beazley
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 39: Decision authority levels
Needs adding to e.g. design etc for beazley
Impact |  | Workstream Leads | Program Directors | Steering Group | Other…
Time (Level 0) | Affect or may affect the Level 0 Plan | ü | ü | ü | 
Time (Level 1) | Affect or may affect the Level 1 Plans | ü | ü | û | 
Scope | Affect Programme Scope | ü | ü | ü | 
RAID | Workstream | ü | û | û | 
RAID | Program Leads | ü | ü | û | 
RAID | Overall Programme | ü | ü | ü | 
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 40: inception phase INCEPTION KEY ACTIVITIES – to be fine tuned
Start-up & Visioning
Technical Architecture and Analysis
Capability & Scope Analysis (Business Architecture)
Implementation Planning
Test Strategy
Understand high level Target Operating Model
Understand current state policy “as-is” Business Processes, supporting data, and supporting technology
Identify key business process re-engineering areas based on business priority, business function and capability, and leading practices
Define Future State “to-be” business processes, supporting data, and supporting technology
Define functional and non-functional requirements for GPAS Implementation
Define high-level operational reporting and analysis requirements
Project Kick-off and On-boarding of Resources
Develop Policy Core Implementation Project Charter and Governance Plan
Update Roles and Responsibilities
Assist with updated Stakeholder Analysis\Setup of Project Management Tools
Develop initial Project Plan – Project Increments, Sprints
Prepare for and conduct Executive Stakeholder visioning session
Provide architectural support based on best-of-breed Enterprise Policy Architecture practices.
Define a Policy Technical Architecture Framework to cover the GW Policy Platform & its related integration points
Facilitate technology alignment with the strategic intent of the business, ensures IT resources are used responsibly & technology architecture related risks are actively managed
Identify and document future state transactions inventory & trigger points.
Define, validate and refine Policy Data Conversion approach to cover – open Policy, closed Policy-in-retention & closed Policy for migration to target system.
Conduct high-level source data profiling to validate the overall approach based on target data model.
Define, validate and refine the legacy system decommissioning approach
Produce a Developer on-boarding kit including tool access, standards information
Define estimates for the Implementation effort for the Policy Core Implementation Project initiatives. Detailed estimates for the Policy Core and related integration components for the Policy Core Implementation Project Implementation Phase.
Detail the timeline and activities to implement the Policy Core platform and its related integration components
Define the dependencies between the various Policy Core Implementation Project initiatives
Set objectives of quality management activities and document the test objectives in a measurable format
Identify the different phases of testing required and define approach and Entry and Exit criteria
Define Test Environment requirements
Define Test Data requirements
Define test process, communication procedures, reporting process and governance procedures for the entire project life cycle.

## Slide 41: Programme governance model We will implement a 3-in-a-box Executive Governance structure including Beazley, Capgemini and Guidewire.
01
Make work visible
02
Trust our teams
Account Executive
Guidewire Executives
Cloud Assurance
Engagement Lead
Assurance Lead
Assurance Architect
Strategic
Programme Sponsor
Account & Delivery Executive
Programme Director
Programme Lead
Delivery Lead
Architects
Functional Leads
Workstream Leads
Programme Test Lead
Scrum Master
Integration Lead
Lead Dev Engineer
Business Analysts
Architects
Dev Engineer
Test Engineer
DevOps
Programme Sponsor
Business & IT Executives
Programme Director
E2E Programme Lead
Product Owners
Business SMEs
Architects
E2E Programme Test Lead
Product Owners
Business SMEs
Architects
Operational
Tactical
Critical Issue Resolution
Contingency Planning and Risk mitigation
Issue Escalation
04
Learn with feedback
Define Strategy
Reviews & Prioritization
Overall delivery oversight
Budget approvals
Dashboard (KPI) Reviews
Resolution of Escalations
Manage Risk/Issues & impact
Capacity Management
Relationship Management
Prioritization
Change Control Board
Project level Reporting
Execution (day-to-day work)
Resolve operational issues
Review Weekly Status
Daily stand-up meetings
Programme Management
Steering Committee
Programme Delivery
Quarterly/Monthly
Monthly/Weekly
Daily/Weekly
Governance
03
Remove friction
Activities
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model

## Slide 42: INCEPTION – BY WEEK STRUCTURE - ILLUSTRATIVE
Week 2
Week N..
Week 11
Week 12
PolicyCenter Overview
PC OOTB Value Chain Flows
Product Model/APD Overview
Beazley Target State Process Flows
Beazley Target State Architecture Diagram
Product Model: Cyber
Product Model: D&O
New Submission
  Rating (incl. Tax & Fees)
  Quote Summary
  Policy Review
  Document Generation
  Document Distribution
Integrations: UWWB, BillingCenter
Policy Change
  Initiation of Policy Change
  Rating (incl. Tax & Fees)
  Document Generation
  Close Options
Integrations: UWWB, BillingCenter, Imburse, DPS
Account & Policy File Summary & Tools
Search
Activity Patterns
History Events
Desktop
Actions
Business Admin
Account
  Name Clearance
  Create New Account
  Broker Validation
  Customer Enrichment
  Sanctions
  Licensing
Integrations: CRM, Producer Management System, External Contact System
New Submission
  Submission Clearance
  New Submission
  Offerings
  Pre-Qualification Questions
  Product Model Selection
Integrations: UWWB
Renewals
  Pre-Renewal Direction
  Automatic vs Manual Renewal
  Claim History
  Payment Status
  UW Referrals & Declines
  Pre-emption
  Rating (incl Tax & Fees)
  Document Generation
  Close Options
Integrations: Imburse, ClaimCenter, BillingCenter, UWWB, DPS
New Submission
  Basic Data Capture
  Claims History
  Risk Data Capture
  UW Referrals & Declines
  Risk Analysis
  Quote Versions
Cancellation
  Schedule Cancellation
  Cancel Now
  Rescind
Reinstate
Rewrite
Integrations: UWWB, ClaimCenter, DPS
Tuesday
(AM: 10-12:30
PM-13:30-17:00)
Wednesday
(AM: 10-12:30
PM-13:30-17:00)
Thursday
(AM: 10-12:30
PM-13:30-17:00)
Document Management
Contact Management
Integration: ClaimCenter, DMS
User Setup
  Roles
  Permissions
Org Structure
  Teams
Policy Change
  Premium vs Non-Premium Impacting MTA
  Out of Sequence MTA
  Pre-emption
Integrations: UWWB
New Submission
  Payment Schedule
  Capture Payment Method
  Bind & Issue
  Close Options
Integrations: UWWB, BillingCenter, Imburse, DPS
Quick Quote
Coinsurance
Reinsurance
Subjectivities
Organization Model
  Groups
  Users
  Roles
  Permissions
  Authority Profiles
  Authority Limits
Teams Tab
Producer
  Producer Codes
  Producer Code Security
  Bulk Producer Change
Week 1
Policy center Overview
Team Introductions
Ways of Working
Workstreams
Foundation Scope
Inception Plan
Roles & Responsibilities;
Product Rationalisation;
Product Roadmap
HL Architecture
Key Decisions
Outstanding Actions
Capability Model (draft)
Project Roadmap
The Inception plan will be shared separately for Beazley’s review and approval showing the day-wise plan

## Slide 43: KEY ROLES - raci
Needs to be updated for beazley – source attached
A | Accountable | Authority and decision making
R | Responsible | Responsible for actualisation of the task
C | Consulted | Engaged stakeholder, consulted in decisions, delivery and approach to enable their input
I | Informed | Informed stakeholder receiving updates and outputs only
Key
Relevant for Pre-Inception
Initial look ahead for future phases
RACI has also been broken down further into detailed responsibility lines. Please see attachment below for further details
Detailed RACI:
Notes: 3 mins
Cloud Assurance – feedback highest standard of code globally. Jointly work with them
GW embedded within the team
Fully connected Delivery teams
Clear points of escalation
Lean/Scalable governance model