## RACI
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
Area |  | Beazley |  | Capg |  | Guidewire
Modernization Program Activities |  | A/R |  | C |  | I
Program planning & delivery
Ways of working for all Programs under Modernization
Procurement Management
Program communications and stakeholder management
SteerCo & Leadership reporting
PMO |  | A/R |  | C |  | I
Risk and Issue Management tracking
Dependency Mangement tracking
Programme Metrics & Milestone tracking
Programme Budget & Invoicing payments tracking
Project infra needs set up coordination & tracking
Deliverables tracking
Requirements Gathering and Management (GPAS & Billing) |  | A |  | R |  | C
Product Backlog refinement and Business process mapping
User story refinement with business rules and acceptance criteria
Requirements sign-off
Prototyping and mock-ups
Workshops schedule, execution & follow-up
Architecture and Technical Management (GPAS and Billing) |  | A/R |  | R |  | R
Confirm Architecture and Design Principles
High level designs
Create and maintain Technical Design Decisions
Low level design
Data Migration Strategy
Environments and Infrastructure |  | A/R |  | C |  | R
Infrastructure and environments planning and provisioning
Deployments, maintainence and supplier issues resolution
Capacity planning & scalability
Security and Compliance implementation
Monitoring, management & performance optimisation
GPAS and Billing Delivery |  | C |  | A/R |  | C
Delivery Management - sprint plan and execution, status reporting, risks/issue logging, risks/issue mitigation within Cap control, recording and monitoring Cap specific dependencies, problem management within Cap control, stakeholder management, change control management affecting Cap scope of work
Develop user stories adhering to Guidewire Cloud standards
Unit testing adhering to Guidewire Cloud Standards
Sprint plan and raising dependencies
Resolve Guidewire Cloud standard assessment observations
Sprint progress reporting
E2E Testing |  | A |  | R |  | I | This is the only section that has been changed for BIDAC
End to End Test Strategy and Execution
JIRA and Confluence set-up
Metrics and Reporting
Risks and Issues management
Non Functional Testing
Defects resolution specific to GPAS & Billing components |  | C |  | A/R |  | C
GPAS and Billing Sprint Testing |  | A |  | R |  | I
Functional test plan, test execution, defects severity and priority validations
Risks, Issues and Dependencies status reporting
JIRA and Confluence set-up
Metrics and Reporting using JIRA
User story demo sign-off
API testing for Inbound and Outbound Integrations identified in the Integration Manifest
Release Management |  | A/R |  | C |  | C
End to end release plan roadmap for the Program
Strategy, Processes and teams for deployments, check points
Third party coordination for all environments
Cutover, Go-live and Post Go-live Support |  | A/R |  | R |  | R
Cut-over plan and Implementation Management
Establish post Go-live Support Model
Infrastructure and environments set-up
Service Design and PGLS Plan
Incident fixes specific to GPAS & Billing during warranty |  | C |  | A/R |  | C
Business Change Management |  | A/R |  | C |  | I
Change Impact assessment and readiness
Business roll-out plan
Communications and reporting
Legacy |  | A/R |  | C |  | I
Management of legacy party stakeholders
Delivery of dependencies as per Program plan
Management of design, build and testing required by GPAS & Billing
Communication on Legacy changes that impact GPAS & Billing
Status updates and reporting
Finance |  | A/R |  | C |  | I
Management of Finance party stakeholders
Delivery of dependencies as per Program plan
Management of design, build and testing required by GPAS & Billing
Communication on Finance changes that impact GPAS & Billing
Status updates and reporting
Documents - Beazley to confirm platform selection and requirements, post which this section to be revised as it is highly likely Capgemini will be asked to do the build |  | A/R |  | C |  | I
Document supplier and platform management
Deliver Document platform dependencies as per Program plan
Documents design
Document template requirements, build and test
Environment and Infrastructure management
Data & Analytics |  | A/R |  | I |  | I
Data Management Strategy
Data & Analytics build and test
Analytics Reporting requirements & build
Dependency management with rest of the Program
App Events - Capgemini to do the assessment on effort required, to be done in parallel to inception
Guidewire Data copy - CDA to Guidewire S3 bucket configuration |  |  |  | R
Guidewire Data copy - Guidewire S3 bucket to Beazley S3 bucket |  |  |  | R
Data movement- Beazley S3 bucket to Beazley Data Layer |  |  |  | I
Third Parties (Integrations & Guidewire) |  | A/R |  | C |  | I
Third party management
Third party deliverables alignment to Program plan
Third party environments management
Issues resolution with Third parties
Status updates and reporting
Policy Data Migration - The current scope of work for Capgemini is Policy Data Migration. The assumption for Policy Data Migration is on-renewal which will not need any work on Billing Migration. Incase of a change in assumption of on-renewal, Beazley to assess the need for additional scope on Billing Migration.
E2E Oversight |  | A/R |  | C |  | I
Legacy Data provisioning (for Dev, Test, SIT and Dry-run)
Legacy Data management (incl. data profiling)
Infrastructure provisioning (for Dev, Test, SIT and secure Data env for Dry-run)
Policy Data Migration Strategy / High-level Design (HLD) |  |  |  | R
Policy Data Migration technical solution
Policy Data Migration mapping and Gap analysis (between Source & Target - GW)
Policy Data Migration implementation and Go-live strategy
UWWB (Underwriting Work Bench) |  | A |  | C |  | I
Requirements management
Deliverables alignment to Program plan
Environments management
Issues resolution impacting Program
Status updates and reporting
GPAS and Billing Integration (Guidewire only) - External (third party) and Internal (Beazley systems) |  | A/R |  | R |  | I
Integrations design
Integrations inventory
High Level Design
Low Level Design
Technical mapping document
Plan, Build and unit test integrations

## Key
Key
A | Accountable | Final overall authority and decision making
R | Responsible | Responsible for actualisation of the task (doing the work)
C | Consulted | Engaged stakeholder, consulted in decisions, delivery and approach to enable their input
I | Informed | Informed stakeholder receiving updates and outputs only