## RACI (2)
Area | High level breakdown | Beazley | Capg | Guidewire
Modernization Programme Activities |  | A | C | I
Program planning & delivery
Ways of working for all programs under Modernization
Procurement Management
Program communications and stakeholder management
SteerCo & Executive Leadership reporting
PMO |  | A | C | I
Risk and Issue Management tracking
Dependency Mangement tracking
Programme Metrics & Milestone tracking
Programme Budget & Invoicing payments tracking
Project infra needs set up coordination & tracking
Deliverables tracking
Requirements Gathering and Management (GPAS & Billing) |  | A | R | C
Product Backlog refinement | Product Model capturing
User story refinement with business rules and acceptance criteria | Feature inventory mapped to business requirements
Requirements sign-off
Prototyping and mock-ups | Product backlog management
Product Backlog to Business process mapping | Functional backlog management
Stakeholders and SME availability and Depedency management | User story definition and business rule capturing
Workshops schedule, execution & follow-up | Business Process mapping (application specific)
Risk review and mitigation actions on complex scenarios of business needs
Target Operating Business process model
End state process design
End to End Journey and UX Design
Target operating model impact assessment and design (interim and end state)
Architecture/Technical Management (GPAS and Billing) |  | A/R | R | R
Confirm Architecture and Design Principles | Confirm Architectural Principles
High level designs | Create Application Architecture Blueprint
Create and maintain Technical Design Decisions | High level designs
Low level design | Technical Design Decisions
Data Migration Strategy | Data Migration Principles
Data Architecture Principles and Design
Environments and Infrastructure |  | A/R | C | R
Infrastructure and environments creation and set-up with connectivity | Environment Planning
Capacity planning & scalability | Environment Provisioning
Security and Compliance implementation | Environment Management
Monitoring, management & performance optimisation | Infrastructure set up and management
Infrastructure scaling
GPAS and Billing Delivery |  | C | A/R | C
Develop user stories adhering to Guidewire Cloud standards | Delivery of User stories and documented requirements
Unit testing adhering to Guidewire Cloud Standards | Implementation of coding standards
Sprint plan and raising dependencies | Unit testing
Resolve Guidewire Cloud standard assessment observations | Automated/G Unit delivery
Sprint progress tracking and reporting
Code Management & Branching strategy
E2E Testing |  | A/R | C | I
Design and Execute an end to end Functional Test Strategy and Governance plan that integrates all systems in the larger Modernization program - including upstream & downstream systems and GPAS & Billing (ex: UWWB, Finance, Data feeds etc) - Functional testing will cover - System Integration testing & User acceptance testing | System Integration Testing
Design and Execute an end to end Non Functional Test Strategy and Governance plan that integrates all systems in the larger Modernization program - including upstream & downstream systems and GPAS & Billing - (diff types of testing could cover - Performance, Penetration, Accessibility, Security, Operational acceptance, Disaster Recovery etc) | User Acceptance Testing
JIRA and Confluence set-up to monitor Test phase preparation and execution | Non Functional Testing
Metrics and Reporting for E2E test plan & execution | Penetration Testing
Align expectation and plans of all stakeholder teams to the overall Test Strategy and plan (includes all third parties outside the Program) | Accessbility Testing
Identify, monitor and resolve risks & issues impacting E2E testing | Diaster Recovery Testing
Identify, monitor and resolve dependencies for all stakeholders | Operational Acceptance Testing
Provide environments and infrastructure along with continous support to meet timelines
Defects resolution? | Reporting and Metrics
GPAS and Billing Functional Testing |  | A | R | I
Design and Execute Functional Test Strategy and Governance for GPAS & Billing only - Functional testing will cover - Sprint Testing, Sprint automation testing, System integration tesing (stabilisation), Regression testing | In Sprint Testing
Design and Execute Integration testing
Provide due deligence findings on right testing tools to be used - example of Guidewire Testing framework vs Selinium
Identify, monitor and report risks & issues impacting GPAS & Billing that originate outside of Capgemini control
Identify, monitor and report dependencies with stakeholders outside Capgemini control
Metrics and Reporting for GPAS & Billing functional test phases upto Stabilisation
Integration Testing
Release Management |  | A | C | C
Preparation of an End to End Release plan for the Modernization Program including GPAS & Billing
Set-up a DevOps team to take-up End to End deployment activities (code promotions, issue resolutions, platform support, monitoring etc) across phases of the Program - Development, System Test (Sprint), System Integration testing (Stabilisation), UAT and other forms of testing
Deploy a framework to enable efficient and effective processes and governance
Coordination and alignment with third parties for end to end release and environment management
Cutover, Go-live and Post Go-live Support |  | A/R | R | R
Prepare and execute Production cut-over strategy and planning for GPAS & Billing and other upstream or downstream systems | Cut over planning
Coordinate and set-up the IT infrastructure and environments for pre-prod, prod and post prod activities | Establish Post Go Live Support Model
Plan and execute post go-live releases | Implementation Management
Incident fixes, unit testing and regression testing | Go-live co-ordination
Service Design
PGLS
Business Change Management |  | A | C | I
Prepare and execute end user roll-out plan for the new GPAS & Billing system
Own the Change Impact and readiness assessments
Define and roll out the Strategy for to-be Business process change to end users including training
Promote Agile maturity, Drive Colloboration across all stakeholder teams
Legacy |  | A/R | C | I
Engage and agree with Legacy teams for alignment to dependencies called out by GPAS & Billing delivery plan - both SME availability and deliverables expected | Management of legacy party stakeholders in Travelers
Stakeholders interaction, alignment of the Legacy teams to ensure smooth execution of GPAS & Billing delivery | Delivery as per the programme plan
Manage, correct or suggest alternate solutions to any data quality issues for data dependencies called out by GPAS & Billing delivery teams | Management of Legacy design, build and testing required by FOS
Provide requested documentation of Legacy systems like - design, constraints, product model information etc | Management and communication of any other changes in the legacy space impacting FOS
Legacy Decommissioning
Finance (Subledger) |  | A/R | C | I
Engage and agree with downstream Finance teams for alignment to dependencies called out by GPAS & Billing delivery plan - both SME availability and deliverables expected | Management of Finance stakeholders in Beazley
Identify, Impact assess, manage and communicate any changes in the Finance downstream that has a potential to impact GPAS & Billing Program plan | Management of any required Finance design, build and testing required in GPAS and Billing
Stakeholders interaction, alignment of the Finance teams to ensure smooth running of GPAS & Billing delivery plan | Management and communication of any other changes in the Finance space impacting GPAS & Billing
Documents |  | A/R | C | I
Choosing apprpriate document management system for GPAS and Billing | Delivery as per the programme plan
Refinement of backlog for GPAS and Billing documents requirement | Document platform management
Build documents & integrate to GPAS & Biling systems | Document supplier management
Align documents build plan to GPAS & Billing plan | Document template requirements, build and test
Plan and execute all related testing both at Sprint, System test and User acceptance | Document design principles
Documents infrastrucutre and environment management
Data & Analytics |  | A/R | I | I
GPAS & Billing data consumption into other Modernization downstream systems and drawing analytics on top of it | Data management strategy
CDA configuration | Requirement gathering and scope confirmation
Producing and managing reporting output and analytics required
Dependency management with wider programme
Implementation of data and analytics changes as required by FOS
Third Parties (Integrations & Guidewire) |  | A/R | C | I
Program Manage full life cycle of third party management
Identify and Establish interactions with all third parties in the Program scope
Align GPAS & Billing devliery plan dependenceis with third party plans
Resolve any gaps in dependencies in the best interest to keep GPAS and Billing dates intact
Define, agree and maintain all contratual requirements with third parties
Data Migration |  | A/R | R | I
Data Migration Strategy | Data Migration Strategy
Data Migration technical solution | Data Migration technical solution
Data Migration mapping and gap analysis | Data Migration mapping and gap analysis
Data Migration implementation and Go-live strategy | Data Migration implementation and Go-live strategy
UWWB (Underwriting Work Bench) |  | A | C | I
Engage and agree with UWWB teams for alignment to dependencies called out by GPAS & Billing delivery plan - both availability and deliverables expected
Identify, Impact assess, manage and communicate any changes in the UWWB that has a potential to impact GPAS & Billing Program plan
Stakeholders interaction, alignment of the Finance teams to ensure smooth running of GPAS & Billing delivery plan
Integration - External and Internal (GPAS and Billing) |  | A/R | R | I
Target state E2E architecture | Target state E2E architecture
Target state integration inventory | Target state integration inventory
High Level Design | High Level Design
Non-functional requirement | Non-functional requirement
Low Level Design | Low Level Design
Produce Mapping document | Produce Mapping document
Build and Development | Build and Development
Unit Testing | Unit Testing
Establish and Test Connectivity | Establish and Test Connectivity

## RACI
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
Area |  | Beazley |  | Capg |  | Guidewire
Modernization Program Activities |  | A |  | C |  | I
Program planning & delivery
Ways of working for all Programs under Modernization
Procurement Management
Program communications and stakeholder management
SteerCo & Leadership reporting
PMO |  | A |  | C |  | I
Risk and Issue Management tracking
Dependency Mangement tracking
Programme Metrics & Milestone tracking
Programme Budget & Invoicing payments tracking
Project infra needs set up coordination & tracking
Deliverables tracking
Requirements Gathering and Management (GPAS & Billing) |  | A |  | R |  | C
Product Backlog refinement and Business process mapping
User story refinement with business rules and acceptance criteria
Requirements sign-off
Prototyping and mock-ups
Workshops schedule, execution & follow-up
Architecture and Technical Management (GPAS and Billing) |  | A/R |  | R |  | R
Confirm Architecture and Design Principles
High level designs
Create and maintain Technical Design Decisions
Low level design
Data Migration Strategy
Environments and Infrastructure |  | A/R |  | C |  | R
Infrastructure and environments planning and provisioning
Deployments, maintainence and supplier issues resolution
Capacity planning & scalability
Security and Compliance implementation
Monitoring, management & performance optimisation
GPAS and Billing Delivery |  | C |  | A/R |  | C
Develop user stories adhering to Guidewire Cloud standards
Unit testing adhering to Guidewire Cloud Standards
Sprint plan and raising dependencies
Resolve Guidewire Cloud standard assessment observations
Sprint progress reporting
E2E Testing |  | A/R |  | C |  | I
End to End Test Strategy and Execution
JIRA and Confluence set-up
Metrics and Reporting
Risks and Issues management
Defects resolution specific to GPAS & Billing components |  | C |  | A/R |  | C
GPAS and Billing Functional Testing |  | A |  | R |  | I
Functional test plan and execution
Risks, Issues and Dependencies status reporting
Metrics and Reporting using JIRA
Release Management |  | A |  | C |  | C
End to end release plan roadmap for the Program
Strategy, Processes and teams for deployments, check points
Third party coordination for all environments
Cutover, Go-live and Post Go-live Support |  | A/R |  | R |  | R
Cut-over plan and Implementation Management
Establish post Go-live Support Model
Infrastructure and environments set-up
Service Design and PGLS Plan
Incident fixes specific to GPAS & Billing during warranty |  | C |  | A/R |  | C
Business Change Management |  | A |  | C |  | I
Change Impact assessment and readiness
Business roll-out plan
Communications and reporting
Legacy |  | A/R |  | C |  | I
Management of legacy party stakeholders
Delivery of dependencies as per Program plan
Management of design, build and testing required by GPAS & Billing
Communication on Legacy changes that impact GPAS & Billing
Status updates and reporting
Finance (Subledger) |  | A/R |  | C |  | I
Management of Finance party stakeholders
Delivery of dependencies as per Program plan
Management of design, build and testing required by GPAS & Billing
Communication on Finance changes that impact GPAS & Billing
Status updates and reporting
Documents |  | A/R |  | C |  | I
Document supplier and platform management
Deliver Document platform dependencies as per Program plan
Documents design
Document template requirements, build and test
Environment and Infrastructure management
Data & Analytics |  | A/R |  | I |  | I
Data Management Strategy
Data & Analytics build and test
Analytics Reporting requirements & build
Dependency management with rest of the Program
CDA
Third Parties (Integrations & Guidewire) |  | A/R |  | C |  | I
Third party management
Third party deliverables alignment to Program plan
Third party environments management
Issues resolution with Third parties
Status updates and reporting
Policy Data Migration
E2E Oversight |  | A/R |  | C |  | I
Legacy Data management
Data Migration Strategy |  |  |  | R
Data Profiling with production data
Data Migration technical solution
Data Migration mapping and gap analysis
Data Migration implementation and Go-live strategy
UWWB (Underwriting Work Bench) |  | A |  | C |  | I
Requirements management
Deliverables alignment to Program plan
Environments management
Issues resolution impacting Program
Status updates and reporting
GPAS and Billing Integration - External (third party) and Internal (Beazley systems) |  | A/R |  | R |  | I
Integrations design
Integrations inventory
High Level Design
Low Level Design
Technical mapping document
Plan, Build and unit test integrations
Note on B128: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should we be specific here about E2E Migration Delivery which will need to sit with Beazley?

## Key
Key
A | Accountable | Final overall authority and decision making
R | Responsible | Responsible for actualisation of the task (doing the work)
C | Consulted | Engaged stakeholder, consulted in decisions, delivery and approach to enable their input
I | Informed | Informed stakeholder receiving updates and outputs only