## Sheet1 (hidden)
Sprint | Duration | Work stream | User stories | Week | Testing activities | Detailed activities | Dependencies | Resources
Sprint 1 | Aug 26 - Sep 26 | Policy center | US D&O Product Model Setup | Week 1 | Sanity test | Create data in CSV format for the kinds of products (List). -> Load it through ADL in GW-> Create test cases for data retrival in GW- Role based scenarios- Relationships | LOB product data Environment- SIT 1 | SI
|  |  | INT- Expose Product Model Definition service |  | Test design | Test the API- Request & response | Data- Synthetic- YAML/ JSON requests, Stub, End point | KA
|  |  | Create Account via Integration |  | Test execution | Account creation scenarios/ combinations- Policy holders-(Joint)- Roles-> Address look up-> Positive & negative | GW instance | NS
|  |  | Update Account via Integration |  | Reports | Updation scenario combinations-> changes to criteria- status- Validate the request & response | JIRA Dashboard | MS
|  |  | View and Manage Account Summary |  | Defects | Change view, save and retrive scenarios | Jira set up | LM
|  |  | Create New Submission – Point of Clearance |  |  | New submission - Pre UW workbench- Quote Binding scenarios- | Data injestion to guidewire
|  | Billing Center |  | Week 1 | Sanity test |  | Environment- SIT 1 | SI
[5 empty] | Test design |  | Data- Synthetic | KA
[5 empty] | Test execution |  | GW instance | NS
[5 empty] | Reports |  | JIRA Dashboard | MS
[5 empty] | Defects |  | Jira set up | LM
|  | Integrations |  | Week 1 | Sanity test |  | Environment- SIT 1 | SI
[5 empty] | Test design |  | Data- Synthetic | KA
[5 empty] | Test execution |  | GW instance | NS
[5 empty] | Reports |  | JIRA Dashboard | MS
[5 empty] | Defects |  | Jira set up | LM
Sprint 2

## Test Plan
Sprint | Duration | Week | Testing activities | User stories | Test Scenarios | Dependencies
Sprint 1 | Aug 26 - Sep 25 | Week 1 | Sanity test | Refer US - PC, BC & Integrations | Refer Test scenarios sheet - PC, BC & Integrations | LOB product data load (ADL) Environment- SIT 1 HLD Design E2E arch. User stories elaborations & Sign off JIRA set up / Estimations Resource / Capacity planning & onboarding Test Data creation Integration stubs, End points, Token ID
|  | Week 1 & 2 | Test design
|  | Week 3 & 4 | Test execution
|  | Week 3 & 4 | Defects
|  | Week 3 & 4 | Reports
Sprint 2 | Sep 26 - Oct 25 | Week 1 | Sanity test
|  | Week 1 & 2 | Test design
|  | Week 3 & 4 | Test execution
|  | Week 3 & 4 | Defects
|  | Week 3 & 4 | Reports

## Sprint 1
Work stream | User stories | Functionalties to be tested | Details (To be validated) | Dependencies | Clarifications
Policy center | US D&O Product Model Setup | As Product Manager, | 1.US Admitted Vendors - BICI - All the 5 products are applicable. 2. US Admitted Vendors - BAIC - Applicable to only one product (Beazley Boardroom Protect (US ML )) 3. US Surplus Vendors - BESI - All the 5 products are applicable. 4. US Surplus Vendors - BUSA - Applicable to 4 products (Not applicable to " Beazley Boardroom Protect (US ML )" | 1. APD - Reduced to 3 products.(waiting for updated Product model). Test sceanarios reviewed with Ramesh. APD and ADL will be deployed to test envi. by the start of Sprint 1. 2. Envi. - SIT 1 - Refer Envi. readyness tracker 3. Product model check list - Review with Peter. 4. Test scenarios - High level design 5. Test execution - Verify JIRA , GT Framework / SOAP UI, Test a scenario, Test dash boards. 6. Anil (PC), Anchal (BC), Sai Keerthi (Integration) - Test scenario walkthrough | There are 16 User stories for Product model set up - All these 16 user stories are part of Sprint 1?
|  | 1. Able to find product | There are 5 products. 1. Advanced Boardroom and Company (US ML ) - 2. Beazley Boardroom Protect (US ML ) 3. Beazley Armour (Armour Boardroom Protect) (US ML & DIC) 4. Beazley Execuguard (US ML) 5. Excess 2014 (Excess product) (Excess) | 1. Finalized Product rationalization sheet. 2. Product document of Guidewire "K" version for reference.(OOTB UI referense, shall we get UI mock up screenshots) 3. Field level mapping document - (Legacy Beazley Pro vs GWPC)
|  | 2. Ability to define Policy line |  |  | What is the Policy line for each product?
|  | 3. Ability to define coverages | Coverages: Total 13 coveragest. 1. Insd Person Liability - Side A - Applicable to all the 5 products. 2, Insd Org Reimbursement - Side B - Applicable to 4 products (otherthan "Beazley Armour (Armour Boardroom Protect) (US ML & DIC)" 3. Insured Organization Liab - Side C - Applicable to 3 products only (Products 1, 2 and 5) 4. Cyber, Crime and PI - These coverages are not applicable to any product. 5. Outside Directors Liability Cover - Applicable to 3 products only (Products 1, 2 and 5) 6. Corporate Legal Liability (CLL) - Not applicable to any product. 7. Commercial Crime - Applicable to only one product (Product# 3) 8. EPL & PTL / Fiduciary - Applicable to 2 Products (Product# 4 and 5) 8. Public Offereing of Securities Insurance & Regulatory Liability - Not applicable to any product. Additional Coverages: 1 additional coverage. Entity Investigation Cover - Applicable to 3 products only (Products 1, 2 and 5) | Coverages and Additional coverages need to be updated in product rationalization sheet.
|  | 4. Able to find state |  |  | Are there any state specific coverages?
|  | 5. Ability to define coverage terms (limits & deductibles) |  |  | In which reference document, we can see limits and deductable classcodes.
6. Ability to define exposures (Class codes)
|  | 7. Ability to define Pre-qualification & Modifiers |  | Pre qualification questions & modifier details required
|  | 8. Validate Conditions |  |  | Cannot find User story for Conditions in Userstory backlogs
|  | 9. Validate Exclusions |  |  | Cannot find User story for Exclusions in Userstory backlogs
10. Ability to set one or multiple currency types for a given Product.
Policy center | Create Account via Integration | The ability to create New Account from Account Tab - New Account or from Actions Menu– Create New Account |  | QA needs to know End point url to create account through integration. (Customer API) | In the User story, it is mentioned as "Create account from Accounts" Tab in PC. But, per Inception workshop notes, it is mentioned as "Confirmed: we will have systematic creation of Account via Integration only within PC, no creating or editing of Account in PC". Which one correct?
|  | The ability to Search for a name by providing Applicant Information |  |  | There are 10 User stories in backlog for Create account. All are in scope for Sprint 1?
The ability to view and navigate to the Account if search returns results.
The ability to do a Name Clearance check to prevent duplication
The ability to create an Account by selecting type Person, Company or retrieve from Address Book
The ability to capture Account Contact Details
The ability to select a Producer using Organization Search
The ability to save the Account information (Update button) and generate an account number
Ability to receive and store Underwriter Assignment to a given Account.
Ability to ingest and surface details of the Customer Hierarchy against an Account within PolicyCenter.
Policy center | Update Account via Integration | As a user, ability to search the MDM for an existing account prior to creating new account in PC |  | End point uirl of MDM API
Ability to ingest notification of Account data update event to trigger the automated update of the Account record in PolicyCenter
Ability to ingest notification of Account data update event to trigger an alert that manual intervention is required to update the impacted Policies policy-level data.
Policy center | View and Manage Account Summary | The ability to view Account File Summary screen
The ability to Edit the Account contact details and add addresses.
The ability to view the Overview information like Account Premium, Loss & Loss Ratio
The ability to recalculate the Overview information
The ability to view the current Activities associated with the account
The ability to navigate to Activity Details tab for a specific activity
|  | The ability to view aggregated Billing information for an account stored in BillingCenter, Next invoice details and last payment details |  |  | Can we see Next invoice details and last pmt details in Billing center in Sprint 1 ?
The ability to navigate to BillingCenter from Account Screen.
The ability to navigate & view Account Billing summary information
The ability to view all Policy Terms associated with this account and filter by its Status
The ability to recalculate the Loss Ratio
The ability to view all the Open Policy Transactions
The ability to navigate to appropriate screen/transaction when a Transaction # or Policy # is clicked.
The ability to navigate to new Policy Submission screen.
The ability to view the Account contacts and roles
The ability to view the Agency/Broker Organization and Producer Code
|  | The ability to view all associated claims to the Account |  | Integration b/w GWPC and Claims system | GWPC is on cloud and Claim Center is OnPerm, how this integration happens? Is this part of Sprint 1?
The ability to view related accounts to the Account if any.
|  | Ability to display an alert to user when a policy associated with a given account is in delinquency |  |  | Is Delinquency functionality in Billing center is Sprint 1 scope?
Policy center | Create New Submission – Point of Clearance/Assignment | Ability to train/inform AI platform (i.e. Cytora) on Master Product Definition within Beazley |  | Need details about AI platform - Cytora
|  | Ability to trigger product selection and Product Model version selection based on set criteria during submission clearance. |  | Solution dicussion pending , per backlog sheet | This happens in pre UW, UWWB or PC? Need clarity.
|  | Ability to trigger Broker Validation logic based on Broker details available. |  | Solution dicussion pending , per backlog sheet | This happens in pre UW, UWWB or PC? Need clarity.
Billing Center | Plans - Billing Plan | As a system admin, | All Sprint 1 Billing center stories can be validated in Admin screens
|  | Able to create new Billing plan |  |  | Per my understanding, we have only Agency Bill for all the products, there is no direct bill. Please confirm.
Able to manage new Billing plan
Able to manage Invoice lead time
Able to manage Invoice fees
Able to manage Disbursements
|  | Able to manage recurring payments through Payment requests | Validate is payment request can be created 12 days before the due date |  | Is it part of Fundation release? Per Backlog doc, this is TBD
Billing Center | Payment plan | As a system admin, I should be able to create and manage new payment plans | Ability to collect premium in full (Annual Payment plan). |  | Per backlog sheet, Annual Payment plan is applicable to 3 products only. Need to know what are those 3 products? For other 2 products, it is installments and it is part of Post fundation release.
Billing Center | Payment Allocation plan | As a system admin
|  | Able to create suspense payment automatically when matching policy is not found |  |  | If extra payment done , then also the exess amout goes to suspense. However, need to confirm if this is also applicable?
Manage suspense by linking it to a policy and invoise
Billing Center | Charge patterns | As s system user,
|  | Ability to display Tax amount and Tax percentage by State or region within BillingCenter |  | Need Charge patterns (product and state specific)
|  | Ability to Invoice tax as one-time charge |  |  | Need to check , how can validate this.
Billing Center | Commission Plan | Should be able to retrieve commission percentages from PC to BC |  | Need Commission percentages
Make policy change in PC and retrive commission percenage changes in BC
|  | Able to handle 0% commission even policy handles by broker |  | Need Broker organization setup
Billing Center | Return Plan |  |  |  | Cannot see any user stories for Return plans in User story backlog sheet
Billing Center | Agency Bill Plan |  |  |  | Cannot see any user stories for Return plans in User story backlog sheet
Billing Center | Broker Organization setup |  |  |  | Cannot see any user stories for Return plans in User story backlog sheet
Integrations | MDA Tech Spike – Connect via APIM |  |  |  | Need details - To be dicussed with integration team
Integrations | MDM Event Configuration from Application (MDA) – Policy |  |  |  | Need details - To be dicussed with integration team
Integrations | PC-BC Integration – Policy (OOTB) | Validate the policy data flow from GWPC to BC
Validate if payment plan and schedule data flow from GWBC to PC
Integrations | Product Model definition service |  |  |  | Need details - To be dicussed with integration team
Integrations | Locate | Validate address standadization service
Integrations | Create/Update Account API updates to new data definition | Ability to create new account |  | QA needs to know End point url to create account through integration. (Customer API)
|  | Ability to update an account |  | End point uirl of MDM API

## Sprint 2
Work stream | User stories | Functionalties to be tested | Details (To be validated) | Dependencies | Clarifications
Policy Center | Create New Submission – Point of Quote | As a PolicyCenter User, should be able to create a Quick Quote so that I can capture minimum set of data to return a Premium against an Indicative/Non-Binding Quote Version which can later be converted to a bindable Quote Version.
|  | As a PolicyCenter User, I should be able to view summary of quote so that I can view Insured Information and Premium Info. | The ability to review the Premium by Coverages, Policy Premium, Taxes & Charges
The ability to view Submission wizard details
Policy Center | Update New Submission - Ingest Additional Quote Versions (UWWB) | The ability to create Side-by-Side Quote versions
he ability to view Premium details on click Quote Button
The ability to Edit Policy Transaction
The ability to select Coverages
The ability to Create multi-version
The ability to Close quote with multiple options
Ability to generate an Indicative Quote to be shared to Broker.
Ability to promote an Indicative Quote version to a full Quote Offer.
Ability to produce a new Quote Version while maintaining an auditable record of previous Quote Versions.
Ability to recognise and maintain a history of the Broker-accepted Quote Version.
The ability to create, store and view side-by-side multiple Quote Options against a single Quote Version
The ability to modify the underwriting company, coverages and coverages selected at a Quote Option level against a signle Quote Version
Policy Center | Forms inference / Document triggers | As a PolicyCenter User, I should be able to view forms so that I can view the related forms applicable for the submission. | Ability to trigger document generation based on set criteria for a given Transaction, Policy and/or Account. | List of applicable forms / documents for each transaction and criteria for document trigger are needed.
|  | Ability to trigger Endorsement documentation generation based on set criteria for a given Transaction. |  | Need criteria for Endorsement document trigger
|  | Ability to trigger Subjectivity documentation based on set criteria for a given Policy Transaction. |  | Need criteria for subjectevity document trigger
Ability to trigger population of Quote documentation template with appropriate values for a given Transaction, Policy and/or Account
Ability to generate Invoice at point of Bind
|  | Ability to generate an Invoice for Customer, Broker and Coinsurer with any required variations. |  |  | What are the variations in invoise generation for customer, Broker and Coinsurer? Where can I check the docuementation.
|  | Ability to trigger population of document at point of Bind |  |  | What are the list of docs when policy is Bind.
|  | Ability to trigger population of document at point of issuance |  |  | What are the list of docs when policy is issued.
|  | Ability to trigger workflow to include appropriate document attachments or document links in e-mail communications to Broker. | Validate if, Binder & Invoice should trigger on Bind; Draft Watermarked Policy Document can be triggered at pre-Issuance (Quote, Bind etc); Policy Documents should trigger on Issuance
|  | Ability to trigger generation and distribution of Broker chasers for in progress transaction prior to system logic performing auto NTU and auto lapse |  |  | when the system logic performs auto NTU and auto lapse.
|  | Ability to trigger generation and distribution of marketing communications or Broker chasers for Lapsed transactions based on set criteria (i.e. Number of days since Lapse etc) |  |  | What is the criteria
Ability to trigger & overlay a 'Draft' watermark to any document generated, to be shared internally or externally to Broker.
Ability to trigger a cancellation document and earned premium invoice when the cancellation Transaction is scheduled or cancelled.
Policy Center | Subjectivities |  |  |  | Cannot see any user stories for Subjectivities in User story backlog sheet
Policy Center | Close options | As a PolicyCenter User, I should be able to close a submission as Withdrawn and capture relevant data for a given Close Option
Ability to set Transaction status to Expired based on parameterised conditions (i.e. Product, Number of Days past Effective Date/since Quoted Date, reason, contact permitted)
Ability to receive and store status and reason (i.e. Decline; Decline Reason) for completed transactions.
|  | Ability to set Transaction status to Not-Taken-Up based on parameterised conditions (i.e. Product, Number of Days past Effective Date/since Quoted Date, reason, competitor selected, etc) | Validate - Manual NTU and Auto NTU
Ability to capture Winning Carrier when respective reason for NTU is selected.
Policy Center | Auto NTU/Lapse | Ability to set Transaction status to Not-Taken-Up based on parameterised conditions (i.e. Product, Number of Days past Effective Date/since Quoted Date, reason, competitor selected, etc) | Validate for auto NTU / Lapse by reasons - product, Number of days past effective date, Number of days since Quoted date, other reason, Competitor selected etc.
Billing Center | Retrieve Billing Instructions | Retrieve Submission Billing instructions from PC : As a system user, I should be able to retrieve Submission Billing instructions from PolicyCenter so that I can create corresponding accounts, policies, contacts, charges, Payment plan and commission within BillingCenter to manage the financial life cycle of the policies | Ability to retrieve and store commission % and/or amount from PolicyCenter to BillingCenter
Ability to retrieve different tax types and amounts from PolicyCenter for invoicing
Ability to capture Primary Broker and AP contact details based on Product Lines, Geography etc
Ability to identify the contact responsible for Tax administration (Beazley or Insured or Broker)
Ability to retrieve, store and display Insured contacts details from PC (including email, phone number & Address details)
The ability to receive and store within BillingCenter, the details of an ‘Accounts Payable Contact’ for a given Broker.
Ability to Invoice Premium & Tax broken down by State/Country
|  | Create and manage Payment instruments: As a system user, I should be able to configure/setup multiple payment methods like EFT/Wire, ACH, and Lockbox in BillingCenter so that I can create and process payments and settlements against the invoices from these payment methods | Ability to configure following Payment methods within BillingCenter - EFT/Wire, ACH, and Lockbox
|  | Retrieve Cancellation Billing instructions from PC : As a system user, I should be able to retrieve Cancellation Billing instructions from PolicyCenter and determine the final return premium within BillingCenter so that I can generate a single invoice that includes net-of-commissions | Ability to calculate the Final Return premium within BillingCenter upon Policy cancellation instructions received from PC
|  | Retrieve Policy change Billing instructions from PC : As a system user, I should be able to retrieve Policy change Billing instructions from PolicyCenter so that I can I can update corresponding accounts, policies, contacts, create / update charges, invoices, payment instruments, override commissions within BillingCenter to manage the financial life cycle of the policies | Ability to manage commission changes as a result of Commission % changes in PolicyCenter during the Policy period
Ability to generate Policy change invoices during Blackout-window period within BillingCenter
Ability to change broker of record from the beginning of policy period and upon midterm adjustment (dependency with PC)
|  | Retrieve Reinstatement Billing instructions from PC : As a system user, I should be able to retrieve Reinstatement Billing instructions from PolicyCenter so that user can view Reinstatement invoices and manage the financial life cycle of the policy | Ability to handle invoicing for reinstatement transactions (reinstatement after no payment cancellation and regular cancellation, invoice should include net-of-commission value)
|  | Retrieve Rewrite Billing instructions from PC : As a system user, I should be able to retrieve Rewrite Billing instructions from PolicyCenter so that I can create corresponding accounts, policies, contacts, charges and other details in BillingCenter to manage the financial life cycle of the policies | Ability to handle invoicing for cancel-rewrite transactions (for the situation where the original invoice was paid or not paid, invoice should include net-of-commission value)
|  | Retrieve Renewal Billing instructions from PC : As a system user, I should be able to retrieve Renewal Billing instructions from PolicyCenter so that I can create accounts, policies, contacts, charges and other details for renewal term within BillingCenter to manage the financial life cycle of the renewed policies | Ability to handle invoicing for renewal transactions (invoice should include net-of-commission value)
Billing Center | Setup Billing Account |  |  |  | Cannot see any user stories for "Setup Billing account" in User story backlog sheet
Billing Center | Policy and Producers | Producer Policies overview : As a Billing user, I should be able view the summary of all the policies attached to Producers, so that I can manage their policies | The ability to view a list of all Policies associated with a given Broker (Producer)
|  | Create and manage Producer Contacts: As a system user, I should be able to retrieve Broker contact details as well as AP contact details from Policycenter so that I view, manage and use the contact details for communication purposes | Ability to capture Primary Broker and AP contact details based on Product Lines, Geography etc. 2 types of contacts - Primary broker contact & AP contact attached to that Broker. Both needs to be retreived into BillingCenter
The ability to receive and store within BillingCenter, the details of an ‘Accounts Payable Contact’ for a given Broker.
Ability to switch on & off sending automated email to Brokers
Ability to select / change the preferred language for documents
|  | Retrieve updated Policy and Producer Contacts: As a system user, I should be able to retrieve updated Policy and/or Broker contacts from Policycenter so that existing contact details are updated in sync with PolicyCenter | Ability to get updated value of billing-related contacts (for example, change of AP contact/commission bank account)
Billing Center | Charges – Premium |  |  |  | Cannot see any user stories for "Charges – Premium" in User story backlog sheet
Billing Center | Taxes |  |  |  | Cannot see any user stories for "Taxes" in User story backlog sheet
Billing Center | Submission Invoicing | As a system user, I should be able to generate individual invoices per policy based on rules once submission transaction is bound in PC so that user can manage the financial lifecycle of the Policy | Ability to populate Beazley Bank details in Invoice documents based on Beazley Entity, Country and Currency
Ability to generate individual invoices per policy
For Policies on Annual Payment plan, ability to generate Invoice on Bind & sent to Broker along with Binder
Ability to set Invoice Due date based on the Lead time (30 days) from date of Bind or Policy effective date whichever is later for New Submission
Ability to Invoice back-dated Policies within BillingCenter
Ability to Invoice Premium & Tax broken down by State/Country
Ability to view amount ‘Written-off' at Invoice item level
Ability to generate the Bill Date of the first invoices as the same date as the Transaction Bound Date
Ability to add notes per instalment
Billing Center | Payment schedule | I should be able to send applicable Payment plans and Payment Schedule details to PolicyCenter during Quote so that Underwriters can view Premium schedule based on Payment plan selected | Ability to send applicable Payment Plans / Payment schedule to PolicyCenter on Quote
Billing Center | Invoicing design |  |  |  | Cannot see any user stories for "Invoice design" in User story backlog sheet
Integrations | Point of ingestion – post clearance/ UWWB assignment – MDA |  |  |  | Need details - To be dicussed with integration team
Integrations | MDM Event – Inbound – Policy / |  |  |  | Need details - To be dicussed with integration team
Integrations | MDM Inbound feed via MDA – Policy |  |  |  | Need details - To be dicussed with integration team
Integrations | CRM Event – Inbound – Policy / |  |  |  | Need details - To be dicussed with integration team
Integrations | CRM Inbound feed via MDA – Policy |  |  |  | Need details - To be dicussed with integration team
Integrations | PC-BC Integration – Billing |  |  |  | Need details - To be dicussed with integration team
Integrations | Agresso Event Configuration – Billing |  |  |  | Need details - To be dicussed with integration team
Integrations | Point of ingestion – Post Quote – MDA/UWWB Part 1 |  |  |  | Need details - To be dicussed with integration team

## TC Count estimates
Sprint# | Stream | User story name | # of TCs | Totals
Sprint 1 | PC | Product model | 50 | 110
|  | Create Account via Integration | 15
|  | Update Account via Integration | 10
|  | View and Manage Account Summary | 25
|  | Create New Submission – Point of Clearance/Assignment | 10
| BC | Plans - Billing Plan | 15 | 80
|  | Payment plan | 10
|  | Payment Allocation plan | 10
|  | Charge patterns | 10
|  | Commission Plan | 10
|  | Return Plan | 10
|  | Agency Bill Plan | 5
|  | Broker Organization setup | 10
| Integrations | MDA Tech Spike – Connect via APIM | 5 | 30
|  | MDM Event Configuration from Application (MDA) – Policy | 5
|  | PC-BC Integration – Policy (OOTB) | 5
|  | Product Model definition service | 5
|  | Locate | 5
|  | Create/Update Account API updates to new data definition | 5
Sprint 2 | PC | Create New Submission – Point of Quote | 15 | 95
|  | Update New Submission - Ingest Additional Quote Versions (UWWB) | 20
|  | Forms inference / Document triggers | 30
|  | Subjectivities | 15
|  | Close options | 10
|  | Auto NTU/Lapse | 5
| BC | Retrieve Billing Instructions | 30 | 125
|  | Setup Billing Account | 5
|  | Policy and Producers | 10
|  | Charges – Premium | 10
|  | Taxes | 10
|  | Submission Invoicing | 20
|  | Payment schedule | 20
|  | Invoicing design | 20
| Integrations | Point of ingestion – post clearance/ UWWB assignment – MDA | 10 | 45
|  | MDM Event – Inbound – Policy / | 5
|  | MDM Inbound feed via MDA – Policy | 5
|  | CRM Event – Inbound – Policy / | 5
|  | CRM Inbound feed via MDA – Policy | 5
|  | PC-BC Integration – Billing | 5
|  | Agresso Event Configuration – Billing | 5
|  | Point of ingestion – Post Quote – MDA/UWWB Part 1 | 5

## Resource estimations
Sprint # | Stream | No. of US | Approx. No. Test cases (Design, Date prep, Execute, Defects) | Approx. No. Testcases per person | Total number people required | Skillset
Sprint 1 | PC | 5 | 110 | 50 | 2 | PC - Functional
| BC | 8 | 80 | 40 | 2 | BC - Functional
| Inetgration | 6 | 30 | 15 | 2 | Integration (GTF & SOAP UI)
| PC & BC |  | 190 | 75 | 3 | Automation (GTF)
Sprint 2 | PC | 6 | 95 | 50 | 2 | PC - Functional
| BC | 8 | 125 | 40 | 3 | BC - Functional
| Inetgration | 8 | 45 | 15 | 3 | Integration (GTF & SOAP UI)
| PC & BC |  | 220 | 75 | 3 | Automation (GTF)
Migration | [5 empty] | ETL

## Resource plan
S.No. | Resource Name | Designation | Grade | Role | Date | Comments
1 | Ninad Durve | Portfolio Manager | D2 | Test Manager (onsite) | 2024-09-02 | Allocated to BZ
2 | Sridhar Illinda | Senior Manager | D1 | Test Manager (Offshore) - PC | 2024-08-16 | Allocated to BZ
3 | Komala K | Consultant | B2 | PC Tester | 2024-08-19 | Available for BZ
4 | Trilochanadevi chodabattula | Associate Consultant | B1 | PC Tester | 2024-08-19 | Available for BZ
5 | Anil Kristipati | Associate Consultant | B1 | PC Tester | 2024-08-26 | Available for BZ
6 | Kavyasree Kalagara | Associate Consultant | B1 | PC Tester | 2024-09-16 | She will join GPAS on 16th Sep
7 | FLP | Software Engg. | A4 | PC Tester | 2024-12-01 | Check if we can oboard 8 weeks early as we get shadow period
8 | Anchal Bohidar | Senior Consultant | C1 | BC Tester | 2024-08-26
9 | Navya Kengam | Associate Consultant | B1 | BC Tester | 2024-10-01
10 | Sandeep Gaikwad | Consultant | B2 | BC Tester | 2024-10-01
11 | FLP | Software Engg. | A4 | BC Tester | 2024-12-01 | Check if we can oboard 8 weeks early as we get shadow period | Sai Keerthi Sheryala
12 | Vijaya Pulidindi | Senior Manager | D1 | Lead - Onsite | 2024-10-14 |  | A Pirithive Raj
13 | Sai Keerthi Sheryala | Associate Consultant | B1 | Integration | 2024-08-19 | Allocated to BZ | Ramesh Babu Boopathy
14 | A Pirithive Raj | Software Engineer | A4 | Integration | 2024-08-12 | Available for BZ. Check for backfill | Manoj Ramisetty
15 | Ramesh Babu Boopathy | Senior Consultant | C1 | Integration | 2024-09-16 |  | Divya S
16 | Manoj Ramisetty | Associate Consultant | B1 | Integration | 2024-10-01 | Till end of Sep, he is in RSA | Rahul Kumar Boddu
17 | Divya S | Consultant | B2 | Integration | 2024-10-01 | Till end of Sep, he is in RSA | Abhiram, J
18 | Rahul Kumar Boddu | Associate Consultant | B1 | Integration | 2024-10-01 | Till end of Sep, he is in UWWB | Sigilambatla, Manoj Kumar
19 | Abhiram, J | Consultant | B2 | Automation | 2024-08-26 |  | Rajendran, Saravanan
20 | Sigilambatla, Manoj Kumar | Sr. Software Engg. | A5 | Automation | 2024-08-26 |  | Sai Satya Narayana Reddy Kovvuri
21 | Rajendran, Saravanan | Consultant | B2 | Automation | 2024-08-26
22 | Sai Satya Narayana Reddy Kovvuri | Consultant | B2 | Automation | 2024-10-01 | Till end of Sep, he is in UWWB
23 | TBD |  |  | Migration Tester
24 | TBD |  |  | Migration Tester
25 | TBD |  |  | Migration Tester
Additional role looking for:
1 auto tester
1 sen tester in PC
1 Integ lead in Onshore
| Kiran Akula | Senior Manager | D1 | Test Manager (Offshore) - BC | 2024-08-16 | Allocated to RSA till 31st Aug. Beazley allocation pending
| Narayanan S | Senior Manager | D1 | Test Manager (onsite) | 2024-04-25 | Allocated to BZ

## Score card
Associate Name | Q1 | Q2 | Q3 | Q4 | Q5 | Score (out of 10) | % of score
Rajendran, Saravanan | 2 | 2 | 0 | 2 | 1 | 7 | 70%
Manoj Kumar Sigalambatla | 0 | 2 | 1 | 0 | 2 | 5 | 50%
Abhiram J | 2 | 0 | 2 | 0 | 2 | 6 | 60%
A Pirithive Raj | 2 | 1 | 2 | 1 | 1 | 7 | 70%
Trilochanadevi chodabattula | 2 | 2 | 1 | 0 | 2 | 7 | 70%
Anchal Bohidar | 2 | 2 | 2 | 0 | 2 | 8 | 80%
Komala K | 2 | 2 | 1 | 0 | 2 | 7 | 70%
Sai Keerthi Sheryala | 2 | 1 | 2 | 2 | 1 | 8 | 80%
Anil Kristipati

## Action items
S. No | Action items | Status
1 | Check the APD - talk to Ramesh | Closed
2 | Request for SOAP UI / Swagger / Postman tools to get in BZ | Closed
3 | Get ready with all the tools required | Closed
4 | Discuss with Dev team (Murali) and plan to test Inbound and Outbound integrations . Need to validate schema and payloads | Closed
5 | Check for stubs availability, If stubs are not given, plan how to do integration testing | Closed
6 | Resources - Need the names , availability dates etc | Closed
7 | To know the BZ Billing center, contact Rupesh (do not disturb Sriram) | Closed
8 | To know about integrations, ask for HLD | Closed
9 | Prepare well and schedule follow up call after a week | Closed
10 | Create Test scripts for OOTB functionality (as asked by Natraj) | In Progress

## Playwright training&script plan
S.No. | Topic | Planned Start Date | Planned End Date | Status | Mentor | Participants | Comments
1 | Playwright Training videos to be shared by Harsha | 2024-08-14 | NA | Closed | NA | NA
2 | Team to go through the videos (This needs to be completed in 3 working days) | 2024-08-16 | 2024-08-20 | Closed | NA | BZ Team Bench Team
3 | Session by Harsha - Typescript VS Javascript | 21-August 2024; 12 to 1 pm | 21 August 2024; 12 to 1 pm | Closed | Harsha | BZ Team Bench Team
4 | GWPOC frame work overview | 21 August 2024; 4 to 5 pm | 21 August 2024; 4 to 5 pm | Closed | Keerthi | BZ Team Bench Team
5 | Identify OOTB use cases & Sprint plan cases | 2024-08-22 | 2024-08-23 | Closed | Sridhar / Kiran/ Harsha / Riya Agarwal | BZ Team Bench Team
6 | Planning meeting and allocation | 2024-08-26 | 2024-08-26 | Closed | Harsha | BZ Team Bench Team
7 | GW PC OOTB cases - Scripting (In allignment to Beazley Sprint plan) | 2024-08-26 | 2024-09-25 | In Progress | Keerthi | BZ Team Bench Team | Based on detailed analysis , planned dates might change, resource allocation to be done
8 | GW BC OOTB cases - Scripting (In allignment to Beazley Sprint plan) | 2024-08-26 | 2024-09-25 | Open | Keerthi | BZ Team Bench Team
9 | Beazley specific items scripting (In allignment to Beazley Sprint plan) | 2024-08-26 | 2024-09-25 | Open | Keerthi | BZ Team Bench Team
10 | Handover the OOTB scripts to Practice |  |  | Open | Harsha | BZ Team Bench Team
Daily stand up call will be conducted for 30 mins to check the status (morning)
Daily code review call will be set up (evenining)
Beazley associates : Abhiram, J j.abhiram@capgemini.com; Rajendran, Saravanan saravanan.saravanan@capgemini.com; Sigilambatla, Manoj Kumar manoj-kumar.sigilambatla@capgemini.com; Sai Keerthi, Sheryala sheryala.sai-keerthi@capgemini.com; A, Pirithive Raj pirithive-raj.a@capgemini.com Ramesh Boopathy Ramesh.Boopathy@beazley.com
Bench associates: M, Sivanpandi sivanpandi.m@capgemini.com; D, Nivetha nivetha.a.d@capgemini.com; Himabindhu, Sayle sayle.himabindhu@capgemini.com; Sri Latha, Sura sura.sri-latha@capgemini.com
Additional associate: riya.b.agrawal@capgemini.com

## Sheet3
| Sprint 1 | Sprint 2
PC | Product model validation for all elements (Products, Coverages, State specific, Conditions, Exclusions etc) | Create New Submission – Point of Quote
| Create Account via Integration | Update New Submission - Ingest Additional Quote Versions (UWWB)
| Update Account via Integration | Forms inference / Document triggers
| View and Manage Account Summary | Subjectivities
| Create New Submission – Point of Clearance/Assignment | Close options
Auto NTU/Lapse
BC | Plans - Billing Plan | Retrieve Billing Instructions
| Payment plan | Setup Billing Account
| Payment Allocation plan | Policy and Producers
| Charge patterns | Charges – Premium
| Commission Plan | Taxes
| Return Plan | Submission Invoicing
| Agency Bill Plan | Payment schedule
| Broker Organization setup | Invoicing design

## Sprint level data
Sprint# | Stream | Total US | Demo Completed | Testing Completed | In progress Test | Blocked | In Dev | Remarks
Sprint 1 | PC | 7 | 7 | 7 |  |  |  |  | 100%
| Integration | 10 | 3 | 10 |  |  |  |  | 100%
| BC | 9 | 9 | 9 |  |  |  |  | 100%
| Total | 26 | 19 | 26 | 0 | 0 | 0 |  | 100%
Sprint 2 | PC | 9 | 8 | 8 |  | 1 |  | Blocked story is with open defect | 88.89%
| Integration | 18 |  | 15 |  | 3 |  |  | 83.33%
| BC | 7 | 6 | 6 |  | 1 |  |  | 85.71%
| Total | 34 | 14 | 29 | 0 | 5 | 0 |  | 85.29%
Sprint 3 | PC | 33 | [6 empty] | 0%
| Integration | 8 | [6 empty] | 0%
| BC | 11 | [6 empty] | 0%
| Total | 52 | 0 | 0 | 0 | 0 | 0 |  | 0%